## Accomplishment Report
UP-Philippine General Hospital
Supply, Delivery, Installation, Testing, and Commissioning of VRF Air-Conditioning for 3rd Floor OR
Taft Avenue, Ermita, Manila 1000 Taft Avenue, Ermita, Manila 1000 UP-Philippine General Hospital Taft Avenue, Ermita, Manila 1000
PROJECT ACCOMPLISHMENT REPORT NO. ____
(For the period ending: (________________________)
Contractor: JEJORS CONSTRUCTION CORPORATION
|  | AWARDED BILL OF QUANTITY |  |  |  |  | PROJECT ACCOMPLISHMENT
Item No. | Description of Work | Unit/s | Qty | Unit Cost | Total Cost | Weighted % | Qty | Unit/s | Total | PREVIOUS | THIS PERIOD | ACCOMPLISHMEN TO DATE | % | Remarks
I | GENERAL REQUIREMENTS
PERMITS, FEES, TAXES AND LICENSES
a. Barangay Permits
b. Local Government Permits
c. BFD Permits
d. DENR Permits
e. Permits and Fees
INSURANCES AND BONDS
a. Guarantee / Warranty Bonds
b. Contractor's All Risk Insurance (CARI)
c. Performance Bond
d. Other Insurances and Bonds
| Mobilization and Demobilization | lot | 1 | 103229 | 103229 | 0.2395% | 1 | lot |  | 0 | 0 | 0 | 0%
Site Management Work
| a. Project Management | lot | 1 | 678976 | 678976 | 1.575% | 1 | lot |  | 0 | 0 | 0 | 0%
| b. Admin Support - Accounting, Procurement, Logistics | lot | 1 | 279580 | 279580 | 0.6486% | 1 | lot |  | 0 | 0 | 0 | 0%
| c.Quality Management | lot | 1 | 279580 | 279580 | 0.6486% | 1 | lot |  | 0 | 0 | 0 | 0%
| d. Engineering Management - Clarifications & Drawings | lot | 1 | 319519 | 319519 | 0.7412% | 1 | lot |  | 0 | 0 | 0 | 0%
Temporary Works
a. Site Office
| b. Warehouse | lot | 1 | 51615 | 51615 | 0.1197% | 1 | lot |  | 0 | 0 | 0 | 0%
| b. Site Office Materials & Communication | lot | 1 | 14747 | 14747 | 0.03421% | 1 | lot |  | 0 | 0 | 0 | 0%
| c. Temporary Tools & Cleaning Materials | lot | 1 | 7374 | 7374 | 0.01711% | 1 | lot |  | 0 | 0 | 0 | 0%
| b. Off-site Barracks - Construction and-or Rent - Electric Consumption - Water Consumption | lot | 1 | 184338 | 184338 | 0.4276% | 1 | lot |  | 0 | 0 | 0 | 0%
Temporary Utilities
a. On-Site Water Consumption
b. On-Site Electric Consumption
Security, Safety and Protection
| a. Safety Officer | lot | 1 | 331807 | 331807 | 0.7697% | 1 | lot |  | 0 | 0 | 0 | 0%
| b. Personal Protective Equipment (PPE's) | lot | 1 | 73735 | 73735 | 0.1711% | 1 | lot |  | 0 | 0 | 0 | 0%
| b. Security Guards | lot | 1
Quality Standard and Control
| a. Shopdrawings, As-built plans for Occupancy including Sign & Seal | lot | 1 | 117976 | 117976 | 0.2737% | 1 | lot |  | 0 | 0 | 0 | 0%
b. Material Testing
Transportation
| a. Manpower Service | lot | 1 | 147470 | 147470 | 0.3421% | 1 | lot |  | 0 | 0 | 0 | 0%
| b. Engineer Transportation | lot | 1 | 110603 | 110603 | 0.2566% | 1 | lot |  | 0 | 0 | 0 | 0%
c. Village Delivery/Gate Pass Fees
III | MECHANICAL WORKS
Mechanical Works
I-A. | AIR CONDITIONING- VRV SYSTEM A
| ACCU- 18HP Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 5.157% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2 HP Wall Mounted VRF A (OR No. 2, PNCOU, OR No.3, OR, Pantry, OR Complex Conference Room) Model: FXAQ50BVM | units | 6 | 55087.34 | 330524.04 | 0.7668% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2.5HP Wall Mounted VRF A (OR No. 2 ENT, OR No. 1 ENT, Chief Nurse, OR Pharmacy) Model: FXAQ63BVM | units | 3 | 56222.86 | 168668.58 | 0.3913% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 6HP ceiling Cassette VRF A (Corridor Near OR No.1, Corridor Near OR No. 2 ENT) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.4061% |  | units | 0 | 0 | 0 | 0 | 0%
Accessories:
| Navigation Wired Controller Model: BRC1E63 | units | 11 | 11760.72 | 129367.92 | 0.3001% |  | units | 0 | 0 | 0 | 0 | 0%
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.1037% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A22T | units | 2 | 4351.47 | 8702.94 | 0.02019% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A33T | units | 2 | 4939.51 | 9879.02 | 0.02292% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A732T | units | 3 | 8232.51 | 24697.53 | 0.05729% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A733T | units | 3 | 14112.87 | 42338.61 | 0.09822% |  | units | 0 | 0 | 0 | 0 | 0%
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.04174% |  | units | 0 | 0 | 0 | 0 | 0%
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.09222% |  | units | 0 | 0 | 0 | 0 | 0%
Copper Pipes - Type L Hard Drawn Pipes
| 1/4" | length/s | 10 | 2120.33 | 21203.3 | 0.04919% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 13 | 2952.35 | 38380.55 | 0.08904% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 14 | 4696.92 | 65756.88 | 0.1525% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 9 | 6775.95 | 60983.55 | 0.1415% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 9 | 8642.33 | 77780.97 | 0.1804% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 2 | 10870.01 | 21740.02 | 0.05043% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 8 | 15566.92 | 124535.36 | 0.2889% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 5 | 21015.33 | 105076.65 | 0.2438% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 4 | 21015.33 | 84061.32 | 0.195% |  | length/s | 0 | 0 | 0 | 0 | 0%
Copper Pipes Insulation 25mm Thick
| 1/4" | length/s | 19 | 433.57 | 8237.83 | 0.01911% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 26 | 441.83 | 11487.58 | 0.02665% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 27 | 516.15 | 13936.05 | 0.03233% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 18 | 629.71 | 11334.78 | 0.02629% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 17 | 708.16 | 12038.72 | 0.02793% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 4 | 784.55 | 3138.2 | 0.00728% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 15 | 846.49 | 12697.35 | 0.02946% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 10 | 896.03 | 8960.3 | 0.02079% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 8 | 896.03 | 7168.24 | 0.01663% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Copper Pipe Fittings | lot | 1 | 57975.92 | 57975.92 | 0.1345% | 1 | lot |  | 0 | 0 | 0 | 0%
| Isolation Ball Valves | pc/s | 22 | 3207.48 | 70564.56 | 0.1637% |  | pc/s | 0 | 0 | 0 | 0 | 0%
| PVC Cladding Works | lot | 1 | 22281.85 | 22281.85 | 0.05169% | 1 | lot |  | 0 | 0 | 0 | 0%
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.06697% |  | pcs |  | 0 | 0 | 0 | 0%
Condensate Drain Pipes
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 39 | 404.15 | 15761.85 | 0.03656% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 22 | 641.83 | 14120.26 | 0.03276% |  | length/s | 0 | 0 | 0 | 0 | 0%
Condensate Drain Pipes Rubber Insulation 1.5 meters
| 3/4'' thick for 32mm pvc | length/s | 77 | 427.67 | 32930.59 | 0.07639% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4'' thick for 50mm pvc | length/s | 43 | 812.57 | 34940.51 | 0.08106% |  | length/s | 0 | 0 | 0 | 0 | 0%
Drain Pump
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 9 | 30473.16 | 274258.44 | 0.6362% |  | pcs |  | 0 | 0 | 0 | 0%
0
Fittings
| Wye Reducer 50 x 32 | pcs | 11 | 192.46 | 2117.06 | 0.004911% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Tee 32mm | pcs | 2 | 53.47 | 106.94 | 0.0002481% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Tee Reducer 50 x 32 | pcs | 2 | 203.15 | 406.3 | 0.0009425% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Elbow 32mm | pcs | 6 | 43.63 | 261.78 | 0.0006073% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Cleanout 50mm | pcs | 4 | 213.84 | 855.36 | 0.001984% |  | pcs | 0 | 0 | 0 | 0 | 0%
RELATED ELECTRICAL WORKS
Rough-ins
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.07313% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit 20mm | m | 586 | 65.87 | 38599.82 | 0.08954% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit Connector 20mm | pcs | 29 | 32.09 | 930.61 | 0.002159% |  | pcs | 0 | 0 | 0 | 0 | 0%
Cables / Wires
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 419 | 80.84 | 33871.96 | 0.07858% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 3.5mm² THHN (5 meters per Unit) | m | 71 | 78.48 | 5572.08 | 0.01293% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 0.007244% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 790.33 | 46629.47 | 0.1082% |  | m | 0 | 0 | 0 | 0 | 0%
for ground:
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 72 | 78.48 | 5650.56 | 0.01311% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 0.008717% |  | m | 0 | 0 | 0 | 0 | 0%
I-B. | CONSUMABLES
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.06449% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.04097% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Rugby | bottle | 21 | 277.99 | 5837.79 | 0.01354% |  | bottle | 0 | 0 | 0 | 0 | 0%
| White Tape | rolls | 42 | 374.22 | 15717.24 | 0.03646% |  | rolls | 0 | 0 | 0 | 0 | 0%
| Threaded rod 3/8 (6 meters) | length/s | 94 | 171.07 | 16080.58 | 0.0373% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 0.001588% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 0.0007943% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 0.007962% |  | gallon | 0 | 0 | 0 | 0 | 0%
| Loop Hangers | pcs | 351 | 42.78 | 15015.78 | 0.03483% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Freon | tank | 6 | 14497.77 | 86986.62 | 0.2018% |  | tank | 0 | 0 | 0 | 0 | 0%
| Nitrogen | tank | 3 | 18175.66 | 54526.98 | 0.1265% |  | tank | 0 | 0 | 0 | 0 | 0%
| Mapp Gas | tank | 11 | 855.33 | 9408.63 | 0.02183% |  | tank | 0 | 0 | 0 | 0 | 0%
| Silver Rod | pcs | 141 | 53.47 | 7539.27 | 0.01749% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 0.0004961% |  | pcs | 0 | 0 | 0 | 0 | 0%
I-C. | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 1.711% | 1 | lot |  | 0 | 0 | 0 | 0%
I-D. | MISCELLANEOUS | lot | 1 | 5684.06 | 5684.06 | 0.01319% | 1 | lot |  | 0 | 0 | 0 | 0%
I-E. | TESTING & COMMISSIONING | lot | 1 | 41291.54 | 41291.54 | 0.09579% | 1 | lot |  | 0 | 0 | 0 | 0%
II.A | AIR CONDITIONING- VRV SYSTEM B
| ACCU- Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 5.157% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2 HP Wall Mounted VRF B (OR No. 1 and 3, OR No. 1 Miyake Eye (2), OR No. 2 NSS(2), OR No. 3 Euro-open (2), OR No. 8 Ortho, NSS/ Pay, Storage Room, OR Complex Conference Room) Model: FXAQ50BVM | units | 10 | 55087.34 | 550873.4 | 1.278% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2.5HP Wall Mounted VRF B ( OR no. 4, 6, 13, 14, 15, OR Pharmacy) Model: FXAQ63BVM | units | 2 | 56222.86 | 112445.72 | 0.2609% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 6HP ceiling Cassette VRF B (Corridor near OR No. 2 NSS, Corridor Near Supply Room) Model: FXFQ140AVM | units | 1 | 87530.69 | 87530.69 | 0.2031% |  | units | 0 | 0 | 0 | 0 | 0%
Accessories:
| Wired Remote Controller Model: BRC1E63 | units | 13 | 11760.72 | 152889.36 | 0.3547% |  | units |  | 0 | 0 | 0 | 0%
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 1 | 22345.37 | 22345.37 | 0.05184% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A22T | units | 6 | 4351.47 | 26108.82 | 0.06057% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A33T | units | 1 | 4939.51 | 4939.51 | 0.01146% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A72T | units | 3 | 8232.51 | 24697.53 | 0.05729% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A73T | units | 2 | 14112.87 | 28225.74 | 0.06548% |  | units | 0 | 0 | 0 | 0 | 0%
| Pipe Size Reducer Model: KHRP26M73TP | units | 2 | 5997.97 | 11995.94 | 0.02783% |  | units | 0 | 0 | 0 | 0 | 0%
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.09222% |  | units | 0 | 0 | 0 | 0 | 0%
Copper Pipes - Type L Hard Drawn Pipes
| 1/4" | length/s | 14 | 2120.33 | 29684.62 | 0.06886% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 11 | 2952.35 | 32475.85 | 0.07534% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 15 | 4696.92 | 70453.8 | 0.1634% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 12 | 6775.95 | 81311.4 | 0.1886% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 13 | 8642.33 | 112350.29 | 0.2606% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 1 | 10870.01 | 10870.01 | 0.02522% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.1806% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 1 | 27039.77 | 27039.77 | 0.06273% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 12 | 27039.77 | 324477.24 | 0.7527% |  | length/s | 0 | 0 | 0 | 0 | 0%
Copper Pipes Insulation 25mm Thick
| 1/4" | length/s | 27 | 433.57 | 11706.39 | 0.02716% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 21 | 441.83 | 9278.43 | 0.02152% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 30 | 516.15 | 15484.5 | 0.03592% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 24 | 629.71 | 15113.04 | 0.03506% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 26 | 708.16 | 18412.16 | 0.04271% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 2 | 784.55 | 1569.1 | 0.00364% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 9 | 846.49 | 7618.41 | 0.01767% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 2 | 1011.66 | 2023.32 | 0.004694% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 24 | 1011.66 | 24279.84 | 0.05633% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Copper Pipe Fittings | lot | 1 | 87733.46 | 87733.46 | 0.2035% | 1 | lot |  | 0 | 0 | 0 | 0%
| Isolation Ball Valves | pc/s | 26 | 3207.48 | 83394.48 | 0.1935% |  | pc/s | 0 | 0 | 0 | 0 | 0%
| PVC Cladding Works | lot | 1 | 8234.77 | 8234.77 | 0.0191% | 1 | lot |  | 0 | 0 | 0 | 0%
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.06697% |  | pcs | 0 | 0 | 0 | 0 | 0%
Condensate Drain Pipes
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 37 | 404.15 | 14953.55 | 0.03469% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 24 | 641.83 | 15403.92 | 0.03573% |  | length/s | 0 | 0 | 0 | 0 | 0%
Condensate Drain Pipes Rubber Insulation 1.5 meters
| 3/4'' thick for 32mm pvc | length/s | 74 | 427.67 | 31647.58 | 0.07342% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4'' thick for 50mm pvc | length/s | 48 | 812.57 | 39003.36 | 0.09048% |  | length/s | 0 | 0 | 0 | 0 | 0%
Drain Pump
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 12 | 30473.16 | 365677.92 | 0.8483% |  | pcs | 0 | 0 | 0 | 0 | 0%
Fittings
| Wye 50mm | pcs | 3 | 213.84 | 641.52 | 0.001488% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Wye Reducer 50 x 32 | pcs | 13 | 192.46 | 2501.98 | 0.005804% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Tee 32mm | pcs | 3 | 53.47 | 160.41 | 0.0003721% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Elbow 32mm | pcs | 6 | 43.63 | 261.78 | 0.0006073% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Cleanout 50mm | pcs | 4 | 213.84 | 855.36 | 0.001984% |  | pcs | 0 | 0 | 0 | 0 | 0%
RELATED ELECTRICAL WORKS
Rough-ins
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.07313% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit | m | 673 | 65.87 | 44330.51 | 0.1028% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit Connector 20mm | pcs | 34 | 32.09 | 1091.06 | 0.002531% |  | pcs | 0 | 0 | 0 | 0 | 0%
Cables / Wires
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 482 | 80.84 | 38964.88 | 0.09039% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 3.5mm² THHN (5 meters per Unit) | m | 94 | 78.48 | 7377.12 | 0.01711% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 5.5mm² THHN (5 meters per Unit) | m | 13 | 115.83 | 1505.79 | 0.003493% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 789.47 | 46578.73 | 0.1081% |  | m | 0 | 0 | 0 | 0 | 0%
for ground:
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 85 | 78.48 | 6670.8 | 0.01548% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 0.008717% |  | m | 0 | 0 | 0 | 0 | 0%
II.B | CONSUMABLES
| Vibration Isolator | pcs | 16 | 1389.91 | 22238.56 | 0.05159% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 6 | 2523.22 | 15139.32 | 0.03512% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Rugby | bottle | 25 | 277.99 | 6949.75 | 0.01612% |  | bottle | 0 | 0 | 0 | 0 | 0%
| White Tape | rolls | 49 | 374.22 | 18336.78 | 0.04254% |  | rolls | 0 | 0 | 0 | 0 | 0%
| Threaded rod 3/8 (6 meters) | length/s | 107 | 171.07 | 18304.49 | 0.04246% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 0.001588% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 0.0007943% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 0.007962% |  | gallon | 0 | 0 | 0 | 0 | 0%
| Loop Hangers | pcs | 402 | 42.78 | 17197.56 | 0.0399% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Freon | tank | 7 | 14497.77 | 101484.39 | 0.2354% |  | tank | 0 | 0 | 0 | 0 | 0%
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.1687% |  | tank | 0 | 0 | 0 | 0 | 0%
| Mapp Gas | tank | 12 | 855.33 | 10263.96 | 0.02381% |  | tank | 0 | 0 | 0 | 0 | 0%
| Silver Rod | pcs | 160 | 53.47 | 8555.2 | 0.01985% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 0.0004961% |  | pcs | 0 | 0 | 0 | 0 | 0%
II.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 1.711% | 1 | lot |  | 0 | 0 | 0 | 0%
II.D | MISCELLANEOUS | lot | 1 | 6640.71 | 6640.71 | 0.01541% | 1 | lot |  | 0 | 0 | 0 | 0%
II.E | TESTING & COMMISIONING | lot | 1 | 47190.33 | 47190.33 | 0.1095% | 1 | lot |  | 0 | 0 | 0 | 0%
III.A | AIR CONDITIONING- VRV SYSTEM C
| ACCU- Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 5.157% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2 HP Wall Mounted VRF C (Storage Room, OR No. 8 Ortho, NSS/Pay, OR No. 9 Plastic Surgery (2) ) Model: FXAQ50BVM | units | 1 | 55087.34 | 55087.34 | 0.1278% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2.5HP Wall Mounted VRF C (OR No. 4, Euro- Endo (2), OR No. 7 Ortho, OR. 12 Pedia, OR No. 10 Pay) Model: FXAQ63BVM | units | 7 | 56222.86 | 393560.02 | 0.913% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 6HP ceiling Cassette VRF C (Corridor near Ortho, Corridor near OR. No. 10, Corridor near NSS/Pay) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.4061% |  | units | 0 | 0 | 0 | 0 | 0%
Accessories:
| Wired Remote Controller Model: BRC1E63 | units | 10 | 11760.72 | 117607.2 | 0.2728% |  | units | 0 | 0 | 0 | 0 | 0%
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.1037% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A33T | units | 2 | 4939.51 | 9879.02 | 0.02292% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A72T | units | 4 | 8232.51 | 32930.04 | 0.07639% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A73T | units | 3 | 14112.87 | 42338.61 | 0.09822% |  | units | 0 | 0 | 0 | 0 | 0%
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.04174% |  | units | 0 | 0 | 0 | 0 | 0%
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.09222% |  | units | 0 | 0 | 0 | 0 | 0%
Copper Pipes - Type L Hard Drawn Pipes
| 1/4" | length/s | 1 | 2120.33 | 2120.33 | 0.004919% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 11 | 2952.35 | 32475.85 | 0.07534% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 2 | 4696.92 | 9393.84 | 0.02179% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 14 | 6775.95 | 94863.3 | 0.2201% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 9 | 8642.33 | 77780.97 | 0.1804% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 1 | 10870.01 | 10870.01 | 0.02522% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.1806% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 3 | 21015.33 | 63045.99 | 0.1463% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 7 | 27039.77 | 189278.39 | 0.4391% |  | length/s | 0 | 0 | 0 | 0 | 0%
Copper Pipes Insulation 25mm Thick
| 1/4" | length/s | 2 | 433.57 | 867.14 | 0.002012% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 21 | 441.83 | 9278.43 | 0.02152% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 4 | 516.15 | 2064.6 | 0.00479% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 27 | 629.71 | 17002.17 | 0.03944% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 17 | 708.16 | 12038.72 | 0.02793% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 2 | 784.55 | 1569.1 | 0.00364% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 10 | 846.49 | 8464.9 | 0.01964% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 5 | 896.03 | 4480.15 | 0.01039% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 13 | 1011.66 | 13151.58 | 0.03051% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Copper Pipe Fittings | lot | 1 | 59135.15 | 59135.15 | 0.1372% | 1 | lot |  | 0 | 0 | 0 | 0%
| Isolation Ball Valves | pc/s | 20 | 3207.48 | 64149.6 | 0.1488% |  | pc/s | 0 | 0 | 0 | 0 | 0%
| PVC Cladding Works | lot | 1 | 19711.72 | 19711.72 | 0.04573% | 1 | lot |  | 0 | 0 | 0 | 0%
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.06697% |  | pcs | 0 | 0 | 0 | 0 | 0%
Condensate Drain Pipes
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 33 | 404.15 | 13336.95 | 0.03094% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 12 | 641.83 | 7701.96 | 0.01787% |  | length/s | 0 | 0 | 0 | 0 | 0%
Condensate Drain Pipes Rubber Insulation 1.5 meters
| 3/4'' thick for 32mm pvc | length/s | 66 | 427.67 | 28226.22 | 0.06548% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4'' thick for 50mm pvc | length/s | 23 | 812.57 | 18689.11 | 0.04336% |  | length/s | 0 | 0 | 0 | 0 | 0%
Drain Pump
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 11 | 30473.16 | 335204.76 | 0.7776% |  | pcs | 0 | 0 | 0 | 0 | 0%
Fittings
| Wye Reducer 50 x 32 | length/s | 7 | 192.46 | 1347.22 | 0.003125% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Tee 32mm | length/s | 6 | 53.47 | 320.82 | 0.0007442% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Elbow 32mm | length/s | 7 | 43.63 | 305.41 | 0.0007085% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Cleanout 50mm | length/s | 2 | 213.84 | 427.68 | 0.0009921% |  | length/s | 0 | 0 | 0 | 0 | 0%
RELATED ELECTRICAL WORKS
Rough-ins
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.07313% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit 20mm | m | 444 | 65.87 | 29246.28 | 0.06785% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit Connector 20mm | pcs | 26 | 32.09 | 834.34 | 0.001936% |  | pcs | 0 | 0 | 0 | 0 | 0%
Cables / Wires
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 291 | 80.84 | 23524.44 | 0.05457% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 3.5mm² THHN (5 meters per Unit) | m | 63 | 78.49 | 4944.87 | 0.01147% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 0.007244% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 789.47 | 46578.73 | 0.1081% |  | m | 0 | 0 | 0 | 0 | 0%
for ground:
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 65 | 78.49 | 5101.85 | 0.01184% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 0.008717% |  | m | 0 | 0 | 0 | 0 | 0%
III.B | CONSUMABLES
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.06449% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.04097% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Rugby | bottle | 15 | 277.99 | 4169.85 | 0.009673% |  | bottle | 0 | 0 | 0 | 0 | 0%
| White Tape | rolls | 30 | 374.22 | 11226.6 | 0.02604% |  | rolls | 0 | 0 | 0 | 0 | 0%
| Threaded rod 3/8 (6 meters) | length/s | 65 | 171.07 | 11119.55 | 0.0258% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 0.001588% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 0.0007943% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 0.007962% |  | gallon | 0 | 0 | 0 | 0 | 0%
| Loop Hangers | pcs | 244 | 42.78 | 10438.32 | 0.02422% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Freon | tank | 5 | 14497.77 | 72488.85 | 0.1682% |  | tank | 0 | 0 | 0 | 0 | 0%
| Nitrogen | tank | 3 | 18175.66 | 54526.98 | 0.1265% |  | tank | 0 | 0 | 0 | 0 | 0%
| Mapp Gas | tank | 8 | 812.57 | 6500.56 | 0.01508% |  | tank | 0 | 0 | 0 | 0 | 0%
| Silver Rod | pcs | 98 | 53.47 | 5240.06 | 0.01216% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 0.0004961% |  | pcs | 0 | 0 | 0 | 0 | 0%
III.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 1.711% | 1 | lot |  | 0 | 0 | 0 | 0%
III.D | MISCELLANEOUS | lot | 1 | 5010.49 | 5010.49 | 0.01162% | 1 | lot |  | 0 | 0 | 0 | 0%
III.E | TESTING & COMMISSIONING | lot | 1 | 38342.14 | 38342.14 | 0.08895% | 1 | lot |  | 0 | 0 | 0 | 0%
IV.A | AIR CONDITIONING- VRV SYSTEM D
| ACCU- Model: RXQ20BYM | units | 3 | 789317.19 | 2367951.57 | 5.493% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2 HP Wall Mounted VRF C (Storage Room, OR No. 8 Ortho, NSS/Pay, OR No. 9 Plastic Surgery (2) ) Model: FXAQ50BVM | units | 6 | 55087.34 | 330524.04 | 0.7668% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 2.5HP Wall Mounted VRF C (OR No. 4, Euro- Endo (2), OR No. 7 Ortho, OR. 12 Pedia, OR No. 10 Pay) Model: FXAQ63BVM | units | 4 | 56222.86 | 224891.44 | 0.5217% |  | units | 0 | 0 | 0 | 0 | 0%
| FCU- 6HP ceiling Cassette VRF C (Corridor near Ortho, Corridor near OR. No. 10, Corridor near NSS/Pay) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.4061% |  | units | 0 | 0 | 0 | 0 | 0%
Accessories:
| Wired Remote Controller Model: BRC1E63 | units | 12 | 11760.72 | 141128.64 | 0.3274% |  | units | 0 | 0 | 0 | 0 | 0%
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.1037% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A22T | units | 4 | 4351.47 | 17405.88 | 0.04038% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A33T | units | 1 | 4939.51 | 4939.51 | 0.01146% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A72T | units | 3 | 8232.51 | 24697.53 | 0.05729% |  | units | 0 | 0 | 0 | 0 | 0%
| Refnet Joints Model: KHRP26A73T | units | 3 | 14112.87 | 42338.61 | 0.09822% |  | units | 0 | 0 | 0 | 0 | 0%
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.04174% |  | units | 0 | 0 | 0 | 0 | 0%
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.09222% |  | units | 0 | 0 | 0 | 0 | 0%
Copper Pipes - Type L Hard Drawn Pipes
| 1/4" | length/s | 8 | 2120.33 | 16962.64 | 0.03935% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 12 | 2952.35 | 35428.2 | 0.08219% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 10 | 4696.92 | 46969.2 | 0.109% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 14 | 6775.95 | 94863.3 | 0.2201% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 16 | 8642.33 | 138277.28 | 0.3208% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 2 | 10870.01 | 21740.02 | 0.05043% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.1806% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 2 | 21015.33 | 42030.66 | 0.0975% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 14 | 27039.77 | 378556.78 | 0.8782% |  | length/s | 0 | 0 | 0 | 0 | 0%
Copper Pipes Insulation 25mm Thick
| 1/4" | length/s | 16 | 433.57 | 6937.12 | 0.01609% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/8" | length/s | 24 | 441.83 | 10603.92 | 0.0246% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1/2" | length/s | 19 | 516.15 | 9806.85 | 0.02275% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 5/8" | length/s | 27 | 629.71 | 17002.17 | 0.03944% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4" | length/s | 31 | 708.16 | 21952.96 | 0.05093% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 7/8" | length/s | 4 | 784.55 | 3138.2 | 0.00728% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-1/8" | length/s | 10 | 846.49 | 8464.9 | 0.01964% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-3/8" | length/s | 4 | 896.03 | 3584.12 | 0.008315% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 1-5/8" | length/s | 27 | 1011.66 | 27314.82 | 0.06337% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Copper Pipe Fittings | lot | 1 | 96659.97 | 96659.97 | 0.2242% |  | lot |  | 0 | 0 | 0 | 0%
| Isolation Ball Valves | pc/s | 24 | 3207.48 | 76979.52 | 0.1786% |  | pc/s | 0 | 0 | 0 | 0 | 0%
| PVC Cladding Works | lot | 1 | 32220 | 32220 | 0.07474% |  | lot |  | 0 | 0 | 0 | 0%
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.06697% |  | pcs | 0 | 0 | 0 | 0 | 0%
Condensate Drain Pipes
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 31 | 404.15 | 12528.65 | 0.02906% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 38 | 641.83 | 24389.54 | 0.05658% |  | length/s | 0 | 0 | 0 | 0 | 0%
Condensate Drain Pipes Rubber Insulation 1.5 meters
| 3/4'' thick for 32mm pvc | length/s | 61 | 427.67 | 26087.87 | 0.06052% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 3/4'' thick for 50mm pvc | length/s | 75 | 812.57 | 60942.75 | 0.1414% |  | length/s | 0 | 0 | 0 | 0 | 0%
Drain Pump
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 10 | 30473.16 | 304731.6 | 0.7069% |  | pcs | 0 | 0 | 0 | 0 | 0%
Fittings
| Wye 50mm | length/s | 2 | 213.84 | 427.68 | 0.0009921% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Wye Reducer 50 x 32 | length/s | 11 | 192.46 | 2117.06 | 0.004911% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Tee 32mm | length/s | 3 | 53.47 | 160.41 | 0.0003721% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Tee Reducer 50 x 32 | length/s | 3 | 203.15 | 609.45 | 0.001414% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Elbow 32mm | length/s | 7 | 43.63 | 305.41 | 0.0007085% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Cleanout 50mm | length/s | 6 | 213.84 | 1283.04 | 0.002976% |  | length/s | 0 | 0 | 0 | 0 | 0%
RELATED ELECTRICAL WORKS
Rough-ins
| liquid-tight metallic flexible conduits 2" | m | 78 | 763.39 | 59544.42 | 0.1381% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit 20mm | m | 654 | 65.87 | 43078.98 | 0.09994% |  | m | 0 | 0 | 0 | 0 | 0%
| Metallic Flexible Conduit Connector 20mm | pcs | 32 | 32.09 | 1026.88 | 0.002382% |  | pcs | 0 | 0 | 0 | 0 | 0%
Cables / Wires
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 472 | 80.84 | 38156.48 | 0.08852% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 3.5mm² THHN (5 meters per Unit) | m | 78 | 77.05 | 6009.9 | 0.01394% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 0.007244% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 38.0mm² THHN (5 meters per Unit) | m | 59 | 938.2 | 55353.8 | 0.1284% |  | m | 0 | 0 | 0 | 0 | 0%
for ground:
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 78 | 75.36 | 5878.08 | 0.01364% |  | m | 0 | 0 | 0 | 0 | 0%
| Wire 14.0mm² THHN (G) (5 meters per Unit) | m | 20 | 311.01 | 6220.2 | 0.01443% |  | m | 0 | 0 | 0 | 0 | 0%
IV.B | CONSUMABLES
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.06449% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.04097% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Rugby | bottle | 24 | 277.99 | 6671.76 | 0.01548% |  | bottle | 0 | 0 | 0 | 0 | 0%
| White Tape | rolls | 47 | 374.22 | 17588.34 | 0.0408% |  | rolls | 0 | 0 | 0 | 0 | 0%
| Threaded rod 3/8 (6 meters) | length/s | 104 | 171.07 | 17791.28 | 0.04127% |  | length/s | 0 | 0 | 0 | 0 | 0%
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 0.001588% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 0.0007943% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 0.007962% |  | gallon | 0 | 0 | 0 | 0 | 0%
| Loop Hangers | pcs | 393 | 42.78 | 16812.54 | 0.039% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Freon | tank | 8 | 14497.77 | 115982.16 | 0.2691% |  | tank | 0 | 0 | 0 | 0 | 0%
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.1687% |  | tank | 0 | 0 | 0 | 0 | 0%
| Mapp Gas | tank | 12 | 812.57 | 9750.84 | 0.02262% |  | tank | 0 | 0 | 0 | 0 | 0%
| Silver Rod | pcs | 158 | 53.47 | 8448.26 | 0.0196% |  | pcs | 0 | 0 | 0 | 0 | 0%
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 0.0004961% |  | pcs | 0 | 0 | 0 | 0 | 0%
IV.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 1.711% | 1 | lot |  | 0 | 0 | 0 | 0%
IV.D | MISCELLANEOUS | lot | 1 | 7277.91 | 7277.91 | 0.01688% | 1 | lot |  | 0 | 0 | 0 | 0%
IV.E | TESTING & COMMISSIONING | lot | 1 | 44240.94 | 44240.94 | 0.1026% | 1 | lot |  | 0 | 0 | 0 | 0%
IV | ELECTRICAL WORKS
Electrical Works
I. | Service Entrance
II. | Feeder
Feeder Wire
| 250mm² THHN | m | 726 | 7092.36 | 5149053.36 | 11.94% |  | m | 0 | 0 | 0 | 0 | 0%
| 200mm² THHN | m | 117 | 5509.16 | 644571.72 | 1.495% |  | m | 0 | 0 | 0 | 0 | 0%
| 38mm² THHN | m | 390 | 1126.48 | 439327.2 | 1.019% |  | m | 0 | 0 | 0 | 0 | 0%
for ground:
| 80mm² THHN | m | 242 | 2129.76 | 515401.92 | 1.196% |  | m | 0 | 0 | 0 | 0 | 0%
| 30mm² THHN | m | 39 | 823.69 | 32123.91 | 0.07452% |  | m | 0 | 0 | 0 | 0 | 0%
| 14mm² THHN | m | 130 | 358.87 | 46653.1 | 0.1082% |  | m | 0 | 0 | 0 | 0 | 0%
Roughing-ins
| 90mm dia. IMC | length/s | 94 | 9301.67 | 874356.98 | 2.028% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 40mm dia. IMC | length/s | 45 | 2672.9 | 120280.5 | 0.279% |  | length/s | 0 | 0 | 0 | 0 | 0%
III. | Panel Board & Pullbox
| DP-Main | Assy | 1 | 772225.45 | 772225.45 | 1.791% |  | Assy | 0 | 0 | 0 | 0 | 0%
Main CB: 1200AT, 3P, 230V, 60Hz, Bolt-on Nema12
Branches: 1 - 700AT, 3P
4 - 125AT, 3P
| PP-System A | Assy | 1 | 125827.11 | 125827.11 | 0.2919% |  | Assy | 0 | 0 | 0 | 0 | 0%
Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12
Branches: 2 - 40AT, 3P
3 - 40AT, 2P
9 - 30AT, 2P
| PP-System B | Assy | 1 | 135268.13 | 135268.13 | 0.3138% |  | Assy | 0 | 0 | 0 | 0 | 0%
Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12
Branches: 1 - 40AT, 3P
2 - 40AT, 2P
11 - 30AT, 2P
| PP-System C | Assy | 1 | 120190.82 | 120190.82 | 0.2788% |  | Assy | 0 | 0 | 0 | 0 | 0%
Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12
Branches: 2 - 40AT, 3P
7 - 40AT, 2P
5 - 30AT, 2P
| PP-System D | Assy | 1 | 131472.25 | 131472.25 | 0.305% |  | Assy | 0 | 0 | 0 | 0 | 0%
Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12
Branches: 3 - 40AT, 3P
4 - 40AT, 2P
8 - 30AT, 2P
| PP-Outdoor | Assy | 1 | 473575.57 | 473575.57 | 1.099% |  | Assy | 0 | 0 | 0 | 0 | 0%
Main CB: 700AT, 3P, 230V, 60Hz, Bolt-on Nema12
Branches: 4 - 150AT, 3P
| Transformer | Assy | 1 | 932598.82 | 932598.82 | 2.163% |  | Assy | 0 | 0 | 0 | 0 | 0%
500KVA Step Down Dry Type Transformer, 480V to 230V, 3P Floor mounted, Indoor Type, 60Hz, Nema1 "TRANSPHIL"
| ECB 1250AT Nema 12 | pc | 1 | 302047.59 | 302047.59 | 0.7007% |  | pc | 0 | 0 | 0 | 0 | 0%
| Pullbox (350mm x 350mm x 200mm) | pc | 5 | 5538.24 | 27691.2 | 0.06424% |  | pc | 0 | 0 | 0 | 0 | 0%
| Wire Gutter | lot | 1 | 32074.68 | 32074.68 | 0.07441% |  | lot |  | 0 | 0 | 0 | 0%
IV. | Mechanical System Power Supply
ECB's
| ECB 150AT, 3P, 230V, Nema3R | pc | 4 | 29019.11 | 116076.44 | 0.2693% |  | pc | 0 | 0 | 0 | 0 | 0%
| ECB 40AT, 3P, 230V, Nema3R | pc | 7 | 11083.84 | 77586.88 | 0.18% |  | pc | 0 | 0 | 0 | 0 | 0%
| ECB 40AT, 2P, 230V, Nema3R | pc | 16 | 9429.22 | 150867.52 | 0.35% |  | pc | 0 | 0 | 0 | 0 | 0%
| ECB 30AT, 2P, 230V, Nema3R | pc | 23 | 9429.22 | 216872.06 | 0.5031% |  | pc | 0 | 0 | 0 | 0 | 0%
Roughing-ins
| 40mm dia. IMC | length/s | 49 | 2672.9 | 130972.1 | 0.3038% |  | length/s | 0 | 0 | 0 | 0 | 0%
| 25mm dia. IMC | length/s | 1003 | 1753.43 | 1758690.29 | 4.08% |  | length/s | 0 | 0 | 0 | 0 | 0%
Boxes
| Junction boxes with cover | pc/s | 195 | 125.85 | 24540.75 | 0.05693% |  | pc/s | 0 | 0 | 0 | 0 | 0%
Wires
| 50mm² THHN | Lm/s | 429 | 1395.9 | 598841.1 | 1.389% |  | Lm/s | 0 | 0 | 0 | 0 | 0%
| 5.5mm² THHN | Lm/s | 6798 | 144.13 | 979795.74 | 2.273% |  | Lm/s | 0 | 0 | 0 | 0 | 0%
for ground:
| 14mm² THHN | Lm/s | 143 | 358.87 | 51318.41 | 0.119% |  | Lm/s | 0 | 0 | 0 | 0 | 0%
| 5.5mm² THHN | Lm/s | 3185 | 144.13 | 459054.05 | 1.065% |  | Lm/s | 0 | 0 | 0 | 0 | 0%
V. | Chipping & Restoration Works (Rough only) | lot | 1 | 145441.09 | 145441.09 | 0.3374% | 1 | lot |  | 0 | 0 | 0 | 0%
VI. | Hangers & Supports | lot | 1 | 174529.31 | 174529.31 | 0.4049% | 1 | lot |  | 0 | 0 | 0 | 0%
VII. | Miscelleneuos | lot | 1 | 87264.66 | 87264.66 | 0.2024% | 1 | lot |  | 0 | 0 | 0 | 0%
VIII. | Testing & Commissioning | lot | 1 | 884818.61 | 884818.61 | 2.053% | 1 | lot |  | 0 | 0 | 0 | 0%
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 100% |  |  | 0 | 0% | 0 | 0 | 0%