## BOQ_DATA_ENTRY
REPUBLIC OF THE PHILLIPINES
PROVINCE OF BUKIDNON
MUNICIPALITY OF TALAKAG
PROJECT: | DESIGN AND BUILD OF TALAKAG GOVERNMENT CENTER
LOCATION: | Barangay 2, Talakag, Bukidnon
SUBJECT: | Program of Works
BID DETAILED COST BREAKDOWN
ITEM # | D E S C R I P T I O N | UNIT | QUANTITY | DIRECT UNIT COST |  |  | TOTAL DIRECT COST | OCM | CP | VAT (5%) | TOTAL INDIRECT COST | UNIT COST | AMOUNT | PERCENTAGE
|  |  |  | MATERIAL | LABOR | EQUIPMENT
[8 empty] | 8% | 8% | 5%
I. | GENERAL REQUIREMENTS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | Mobilization/Demobilization | lot | 1 | 816000 | 545940 | 158000 | 1519940 | 121595.2 | 121595.2 | 88156.52 | 331346.92 | 1851286.92 | 1851286.92 | 0.3368%
2 | Safety and Health | lot | 1 | 367750 | 324000 | 0 | 691750 | 55340 | 55340 | 40121.5 | 150801.5 | 842551.5 | 842551.5 | 0.1533%
3 | Survey & Soil Testing | lot | 1 | 140000 | 0 | 0 | 140000 | 11200 | 11200 | 8120 | 30520 | 170520 | 170520 | 0.03102%
4 | Material Testing | lot | 1 | 525552.3 | 0 | 0 | 525552.3 | 42044.184 | 42044.184 | 30482.0334 | 114570.4014 | 640122.7014 | 640122.7014 | 0.1164%
5 | Permit & Licenses | lot | 1 | 450000 | 0 | 0 | 450000 | 36000 | 36000 | 26100 | 98100 | 548100 | 548100 | 0.09971%
6 | Main Power Line | lot | 1 | 2100000 | 0 | 0 | 2100000 | 168000 | 168000 | 121800 | 457800 | 2557800 | 2557800 | 0.4653%
II. | EARTHWORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | STRUCTURE EXCAVATION | cu.m | 4016.205 | 0 | 22.104 | 148.1498 | 683774 | 54701.92 | 54701.92 | 39658.892 | 149062.732 | 207.3691 | 832836.732 | 0.1515%
2 | BACKFILL & COMPACTION | cu.m | 3226.4866 | 0 | 32.3696 | 211.3754 | 786440 | 62915.2 | 62915.2 | 45613.52 | 171443.92 | 296.8814 | 957883.92 | 0.1742%
3 | GRAVEL BEDDING | cu.m | 870.0039 | 1150 | 18.0068 | 124.1374 | 1124170.5195 | 89933.6416 | 89933.6416 | 65201.8901 | 245069.1733 | 1573.8316 | 1369239.6928 | 0.2491%
4 | EARTHFILLING | cu.m | 1598.2026 | 660 | 19.2216 | 112.6265 | 1265533.7358 | 101242.6989 | 101242.6989 | 73400.9567 | 275886.3544 | 964.471 | 1541420.0902 | 0.2804%
5 | SOIL POISONING | units | 581 | 160 | 0 | 0 | 92960 | 7436.8 | 7436.8 | 5391.68 | 20265.28 | 194.88 | 113225.28 | 0.0206%
III. | CONCRETE WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | STRUCTURAL CONCRETE | cu.m. | 2464.8845 | 5200.2436 | 823.7903 | 268.9781 | 15511548 | 1240923.84 | 1240923.84 | 899669.784 | 3381517.464 | 7664.8886 | 18893065.464 | 3.437%
IV. | REINFORCING STEEL BARS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | REINFORCING STEEL BARS | kgs. | 470437.0977 | 66 | 5.8411 | 2.1937 | 34828720.4452 | 2786297.6356 | 2786297.6356 | 2020065.7858 | 7592661.0571 | 90.1744 | 42421381.5023 | 7.717%
V. | FORMWORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | FORMWORKS AND SCAFFOLDING | sq.m. | 3636.312 | 450 | 298.1548 | 0 | 2720524.4 | 217641.952 | 217641.952 | 157790.4152 | 593074.3192 | 911.2526 | 3313598.7192 | 0.6028%
VI. | STRUCTURAL STEEL | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | STEEL STRUCTURE | kgs | 863268.8 | 111.7571 | 24.9872 | 11.9774 | 128386875.48 | 10270950.0384 | 10270950.0384 | 7446438.7778 | 27988338.8546 | 181.1431 | 156375214.3346 | 28.45%
VII. | MASONRY WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | EXTERIOR WALL | sq.m | 4791.0106 | 714.4293 | 219.2909 | 78.2716 | 4848463.5267 | 387877.0821 | 387877.0821 | 281210.8845 | 1056965.0488 | 1232.606 | 5905428.5755 | 1.074%
2 | INTERIOR WALL | sq.m | 6966.556 | 511.2855 | 219.5791 | 78.3745 | 5637609.0291 | 451008.7223 | 451008.7223 | 326981.3237 | 1228998.7683 | 985.6531 | 6866607.7974 | 1.249%
3 | 3D Wall Panel | sq.m | 1846.644 | 712.6368 | 200.266 | 6.4983 | 1697806.4 | 135824.512 | 135824.512 | 98472.7712 | 370121.7952 | 1119.8305 | 2067928.1952 | 0.3762%
4 | Cement Plastering Works | sq.m | 23515.1332 | 112.5339 | 222.7811 | 60.2165 | 9300978 | 744078.24 | 744078.24 | 539456.724 | 2027613.204 | 481.7575 | 11328591.204 | 2.061%
VIII. | FINISHES | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | Ceiling Works | sq.m. | 6731.36 | 965.172 | 199.1862 | 0 | 7837714 | 627017.12 | 627017.12 | 454587.412 | 1708621.652 | 1418.1882 | 9546335.652 | 1.737%
2 | Aluminum Composite Panel | sq.m. | 984.54 | 2300 | 205.562 | 0 | 2466826 | 197346.08 | 197346.08 | 143075.908 | 537768.068 | 3051.7745 | 3004594.068 | 0.5466%
3 | Tileworks | sq.m. | 10549.3694 | 1119.6098 | 259.9207 | 0 | 14553177.87 | 1164254.2296 | 1164254.2296 | 844084.3165 | 3172592.7757 | 1680.2683 | 17725770.6457 | 3.224%
4 | Railings | l.m | 415.28 | 4496.4416 | 1335.7975 | 0 | 2422012.25 | 193760.98 | 193760.98 | 140476.7105 | 527998.6705 | 7103.6672 | 2950010.9205 | 0.5366%
5 | Phenolic Partition (toilets) | lot | 257.08 | 6757.8186 | 2027.0344 | 0 | 2258410 | 180672.8 | 180672.8 | 130987.78 | 492333.38 | 10699.9509 | 2750743.38 | 0.5004%
6 | Interior Wall Finishes | lot | 1 | 10029895.3 | 3004370 | 0 | 13034265.3 | 1042741.224 | 1042741.224 | 755987.3874 | 2841469.8354 | 15875735.1354 | 15875735.1354 | 2.888%
7 | Painting Works | sq.m | 31600.7644 | 174.442 | 299.5507 | 0 | 14978530 | 1198282.4 | 1198282.4 | 868754.74 | 3265319.54 | 577.323 | 18243849.54 | 3.319%
8 | Doors & Windows | lot | 787.5834 | 5274.5797 | 1044.4608 | 0 | 4976771.4 | 398141.712 | 398141.712 | 288652.7412 | 1084936.1652 | 7696.5913 | 6061707.5652 | 1.103%
9 | Façade Glass Works | sq.m | 513.8 | 6000 | 1200.7591 | 0 | 3699750 | 295980 | 295980 | 214585.5 | 806545.5 | 8770.5245 | 4506295.5 | 0.8197%
10 | Carpentry Works | lot | 1 | 461179.4 | 137100 | 0 | 598279.4 | 47862.352 | 47862.352 | 34700.2052 | 130424.9092 | 728704.3092 | 728704.3092 | 0.1326%
11 | Signages | lot | 1 | 450000 | 92455 | 0 | 542455 | 43396.4 | 43396.4 | 31462.39 | 118255.19 | 660710.19 | 660710.19 | 0.1202%
12 | Steel Column & Beam Cladding | lot | 1 | 2361525 | 470680 | 0 | 2832205 | 226576.4 | 226576.4 | 164267.89 | 617420.69 | 3449625.69 | 3449625.69 | 0.6275%
IX. | THERMAL PROTECTION | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | GI Colored Roofing w/ Insulation Foam | sq.m. | 4017.985 | 900 | 0 | 0 | 3616186.5 | 289294.92 | 289294.92 | 209738.817 | 788328.657 | 1096.2 | 4404515.157 | 0.8012%
2 | Sandwich Panel 75mm | sq.m. | 1309.5 | 1656 | 198.9729 | 0 | 2429087 | 194326.96 | 194326.96 | 140887.046 | 529540.966 | 2259.357 | 2958627.966 | 0.5382%
3 | Underground Cistern | sq.m. | 188.8 | 250 | 133.554 | 0 | 72415 | 5793.2 | 5793.2 | 4200.07 | 15786.47 | 467.1688 | 88201.47 | 0.01604%
4 | Toilet Floors | sq.m. | 1689.4582 | 250 | 248.7484 | 0 | 842614.55 | 67409.164 | 67409.164 | 48871.6439 | 183689.9719 | 607.4755 | 1026304.5219 | 0.1867%
X. | PLUMBING WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | Rounghing Ins | lot | 1 | 2384484.9 | 707110 | 0 | 3091594.9 | 247327.592 | 247327.592 | 179312.5042 | 673967.6882 | 3765562.5882 | 3765562.5882 | 0.685%
2 | Fixtures | lot | 1 | 2652262 | 786945 | 0 | 3439207 | 275136.56 | 275136.56 | 199474.006 | 749747.126 | 4188954.126 | 4188954.126 | 0.762%
XI | ELECTRICAL WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | Electrical Roughing ins | lot | 1 | 24582903.85 | 7376625 | 0 | 31959528.85 | 2556762.308 | 2556762.308 | 1853652.6733 | 6967177.2893 | 38926706.1393 | 38926706.1393 | 7.081%
2 | Lighting Fixtures | lot | 1 | 3406407 | 1014540 | 0 | 4420947 | 353675.76 | 353675.76 | 256414.926 | 963766.446 | 5384713.446 | 5384713.446 | 0.9795%
XII. | MECHANICAL WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | Aircon System | lot | 1 | 13940004.4 | 808890 | 0 | 14748894.4 | 1179911.552 | 1179911.552 | 855435.8752 | 3215258.9792 | 17964153.3792 | 17964153.3792 | 3.268%
2 | Fire Protection - Fixtures | lot | 1 | 1125640 | 438720 | 0 | 1564360 | 125148.8 | 125148.8 | 90732.88 | 341030.48 | 1905390.48 | 1905390.48 | 0.3466%
3 | Fire Protection - Roughing Ins | lot | 1 | 3668306.508 | 3318350 | 0 | 6986656.508 | 558932.5206 | 558932.5206 | 405226.0775 | 1523091.1187 | 8509747.6267 | 8509747.6267 | 1.548%
4 | Elevator | lot | 1 | 2359528 | 947430 | 0 | 3306958 | 264556.64 | 264556.64 | 191803.564 | 720916.844 | 4027874.844 | 4027874.844 | 0.7327%
XIII. | ELECTRONIC WORKS | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | CCTV STSTEM | lot | 1 | 1242600 | 726630 | 0 | 1969230 | 157538.4 | 157538.4 | 114215.34 | 429292.14 | 2398522.14 | 2398522.14 | 0.4363%
2 | PABX SYSTEM | lot | 1 | 392400 | 210125 | 0 | 602525 | 48202 | 48202 | 34946.45 | 131350.45 | 733875.45 | 733875.45 | 0.1335%
3 | FDAS SYSTEM | lot | 1 | 2485200 | 1069380 |  | 3554580 | 284366.4 | 284366.4 | 206165.64 | 774898.44 | 4329478.44 | 4329478.44 | 0.7876%
4 | STRUCTURED CABLING | lot | 1 | 2891515.44 | 658080 |  | 3549595.44 | 283967.6352 | 283967.6352 | 205876.5355 | 773811.8059 | 4323407.2459 | 4323407.2459 | 0.7865%
5 | ACCESS POINT SYSTEM | lot | 1 | 1248608.94 | 395035 |  | 1643643.94 | 131491.5152 | 131491.5152 | 95331.3485 | 358314.3789 | 2001958.3189 | 2001958.3189 | 0.3642%
6 | PA SYSTEM | lot | 1 | 2037204.06 | 973410 |  | 3010614.06 | 240849.1248 | 240849.1248 | 174615.6155 | 656313.8651 | 3666927.9251 | 3666927.9251 | 0.6671%
XIV. | EXTERIOR DEVELOPMENT | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | CLEARING & GRUBBING | ha | 3.185 | 0 | 13116.4835 | 175824.1758 | 601776 | 48142.08 | 48142.08 | 34903.008 | 131187.168 | 230129.7231 | 732963.168 | 0.1333%
2 | STRUCTURE EXCAVATION | cu.m | 726.516 | 0 | 25.3704 | 144.5254 | 123432 | 9874.56 | 9874.56 | 7159.056 | 26908.176 | 206.9331 | 150340.176 | 0.02735%
3 | EARTHFILLING | cu.m | 671.14 | 660 | 15.5616 | 107.2802 | 525396.4 | 42031.712 | 42031.712 | 30472.9912 | 114536.4152 | 953.5012 | 639932.8152 | 0.1164%
4 | SUBGRADE PREPARATION, COMMON MATERIAL | sq.m | 3813.14 | 0 | 2.0542 | 14.1616 | 61833 | 4946.64 | 4946.64 | 3586.314 | 13479.594 | 19.7508 | 75312.594 | 0.0137%
5 | AGGREGATE SUBBASE COURSE | cu.m | 762.628 | 1036.1539 | 20.5421 | 141.6156 | 913866 | 73109.28 | 73109.28 | 53004.228 | 199222.788 | 1459.5436 | 1113088.788 | 0.2025%
6 | PORTLAND CEMENT CONCRETE PAVEMENT | sq.m | 6163.14 | 1166.5942 | 304.2994 | 15.0897 | 9158323.5045 | 732665.8804 | 732665.8804 | 531182.7633 | 1996514.524 | 1809.9277 | 11154838.0285 | 2.029%
7 | PARKING AREA | sq.m | 650 | 857.4615 | 118.8062 | 13.8462 | 643574 | 51485.92 | 51485.92 | 37327.292 | 140299.132 | 1205.9587 | 783873.132 | 0.1426%
8 | SIDEWALK | sq.m | 1302 | 826.9324 | 152.2949 | 2.3041 | 1277954 | 102236.32 | 102236.32 | 74121.332 | 278593.972 | 1195.5054 | 1556547.972 | 0.2832%
9 | CONCRETE CURB & GUTTER | lm | 896 | 1300.9152 | 411.4286 | 87.0536 | 1612260 | 128980.8 | 128980.8 | 93511.08 | 351472.68 | 2191.6659 | 1963732.68 | 0.3572%
10 | PAVERS | sq.m | 973.5 | 1050.3338 | 145.1587 | 0 | 1163812 | 93104.96 | 93104.96 | 67501.096 | 253711.016 | 1456.1099 | 1417523.016 | 0.2579%
11 | SOFTSCAPE | sq.m | 11752.04 | 150 | 0 | 0 | 1762806 | 141024.48 | 141024.48 | 102242.748 | 384291.708 | 182.7 | 2147097.708 | 0.3906%
12 | RCPC 600MM | lm | 842 | 2774.3468 | 342.9549 | 741.0926 | 3248768 | 259901.44 | 259901.44 | 188428.544 | 708231.424 | 4699.5243 | 3956999.424 | 0.7198%
13 | CATCH BASIN | units | 24 | 5000 | 2048 | 0 | 169152 | 13532.16 | 13532.16 | 9810.816 | 36875.136 | 8584.464 | 206027.136 | 0.03748%
14 | MANHOLE | units | 29 | 57314.74 | 7344 | 3000 | 1962103.46 | 156968.2768 | 156968.2768 | 113802.0007 | 427738.5543 | 82408.3453 | 2389842.0143 | 0.4347%
15 | STREET LIGHTS | sets | 43 | 35000 | 3586.6047 | 4395.3488 | 1848224 | 147857.92 | 147857.92 | 107196.992 | 402912.832 | 52352.0193 | 2251136.832 | 0.4095%
XV. | CONSTRUCTION OF GUARDHOUSE | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | CONSTRUCTION OF GUARDHOUSE | lot | 1 | 84153.8 | 22032 | 24000 | 130185.8 | 10414.864 | 10414.864 | 7550.7764 | 28380.5044 | 158566.3044 | 158566.3044 | 0.02884%
XVI. | CONSTRUCTION OF MATERIAL RECOVERY FACILITY | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | CONSTRUCTION OF MATERIAL RECOVERY FACILITY | lot | 1 | 89828 | 14688 | 12000 | 116516 | 9321.28 | 9321.28 | 6757.928 | 25400.488 | 141916.488 | 141916.488 | 0.02582%
XVII. | CONSTRUCTION OF SEWAGE TREATMENT PLANT | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | CONSTRUCTION OF SEWARAGE TREATMENT PLANT | lot | 1 | 3935000 | 0 | 0 | 3935000 | 314800 | 314800 | 228230 | 857830 | 4792830 | 4792830 | 0.8719%
XVIII. | CONSTRUCTION OF COFFEE SHOP | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | EXCAVATION WORKS | cu.m | 62.973 | 0 | 48.7828 | 95.2789 | 9072 | 725.76 | 725.76 | 526.176 | 1977.696 | 175.4672 | 11049.696 | 0.00201%
2 | GRAVEL BEDDING | cu.m | 30.5395 | 1150 | 683.9667 | 392.9337 | 68008.425 | 5440.674 | 5440.674 | 3944.4887 | 14825.8367 | 2712.3647 | 82834.2617 | 0.01507%
3 | EARTHFILLING | cu.m | 58.75 | 632.5 | 622.1957 | 357.4468 | 94713.375 | 7577.07 | 7577.07 | 5493.3758 | 20647.5157 | 1963.5896 | 115360.8907 | 0.02099%
4 | CONCRETE WORKS | cu.m | 38.7505 | 5200 | 237.1066 | 77.4184 | 213690.6 | 17095.248 | 17095.248 | 12394.0548 | 46584.5508 | 6716.6914 | 260275.1508 | 0.04735%
5 | REINFORCING STEEL BARS | kgs | 5812.575 | 63 | 6.8713 | 3.0967 | 424132.225 | 33930.578 | 33930.578 | 24599.6691 | 92460.825 | 88.8751 | 516593.0501 | 0.09397%
6 | MASONRY WORKS | sq.m | 45.9 | 874.5277 | 366.2309 | 130.719 | 62950.8213 | 5036.0657 | 5036.0657 | 3651.1476 | 13723.279 | 1670.4597 | 76674.1003 | 0.01395%
7 | PLASTERING WORKS | sq.m | 91.8 | 125.2723 | 275.5773 | 65.3595 | 42798 | 3423.84 | 3423.84 | 2482.284 | 9329.964 | 567.8427 | 52127.964 | 0.009483%
8 | STEEL STRUCTURE | kgs | 9402.1315 | 114.0841 | 31.3665 | 15.7666 | 1515786.1272 | 121262.8902 | 121262.8902 | 87915.5954 | 330441.3757 | 196.3627 | 1846227.503 | 0.3358%
9 | ROOFING WORKS | sq.m | 248.6 | 900 | 0 | 0 | 223740 | 17899.2 | 17899.2 | 12976.92 | 48775.32 | 1096.2 | 272515.32 | 0.04957%
10 | CEILING WORKS | kgs | 13234.88 | 114.0356 | 31.5675 | 14.0009 | 2112339.632 | 168987.1706 | 168987.1706 | 122515.6987 | 460490.0398 | 194.3977 | 2572829.6718 | 0.468%
11 | PAINTING WORKS | sq.m | 192 | 180.2083 | 297.5625 | 0 | 91732 | 7338.56 | 7338.56 | 5320.456 | 19997.576 | 581.9249 | 111729.576 | 0.02032%
12 | DOORS & WINDOWS | sq.m | 34.4 | 5148.375 | 1954.6512 | 0 | 244344.1 | 19547.528 | 19547.528 | 14171.9578 | 53267.0138 | 8651.4859 | 297611.1138 | 0.05414%
13 | FLOOR FINISHES | sq.m | 307.4 | 1120.6246 | 82.0267 | 0 | 369695 | 29575.6 | 29575.6 | 21442.31 | 80593.51 | 1464.8292 | 450288.51 | 0.08191%
14 | PLUMBING WORKS | lot | 1 | 10200 | 4161 | 0 | 14361 | 1148.88 | 1148.88 | 832.938 | 3130.698 | 17491.698 | 17491.698 | 0.003182%
15 | ELECTRICAL WORKS | lot | 1 | 172039.2582 | 50430 | 0 | 222469.2582 | 17797.5407 | 17797.5407 | 12903.217 | 48498.2983 | 270967.5565 | 270967.5565 | 0.04929%
X1X. | CONSTRUCTION OF NEGOSYO & TOURISM CENTER | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | EXCAVATION WORKS | cu.m | 104.388 | 0 | 25.0125 | 57.4779 | 8611 | 688.88 | 688.88 | 499.438 | 1877.198 | 100.4732 | 10488.198 | 0.001908%
2 | GRAVEL BEDDING | cu.m | 35.408 | 1150 | 73.7404 | 254.1798 | 52330.2 | 4186.416 | 4186.416 | 3035.1516 | 11407.9836 | 1800.1069 | 63738.1836 | 0.01159%
3 | EARTHFILLING | cu.m | 59.425 | 632.5 | 43.9377 | 302.9028 | 58197.3125 | 4655.785 | 4655.785 | 3375.4441 | 12687.0141 | 1192.8368 | 70884.3266 | 0.01289%
4 | CONCRETE WORKS | cu.m | 56.407 | 5200 | 977.3255 | 319.1093 | 366444.4 | 29315.552 | 29315.552 | 21253.7752 | 79884.8792 | 7912.6576 | 446329.2792 | 0.08119%
5 | REINFORCING STEEL BARS | kgs | 7332.91 | 63 | 6.536 | 2.4547 | 527901.33 | 42232.1064 | 42232.1064 | 30618.2771 | 115082.4899 | 87.6847 | 642983.8199 | 0.117%
6 | MASONRY WORKS | sq.m | 317.97 | 553.7763 | 237.8998 | 84.9137 | 278729.2383 | 22298.3391 | 22298.3391 | 16166.2958 | 60762.9739 | 1067.6863 | 339492.2122 | 0.06176%
7 | PLASTERING WORKS | sq.m | 635.94 | 113.2182 | 258.5731 | 61.3265 | 275437 | 22034.96 | 22034.96 | 15975.346 | 60045.266 | 527.5376 | 335482.266 | 0.06103%
8 | STEEL STRUCTURE | kgs | 10082.336 | 114.3145 | 25.0091 | 14.7029 | 1552947.6304 | 124235.8104 | 124235.8104 | 90070.9626 | 338542.5834 | 187.6044 | 1891490.2138 | 0.3441%
9 | ROOFING WORKS | sq.m | 220.88 | 900 | 0 |  | 198792 | 15903.36 | 15903.36 | 11529.936 | 43336.656 | 1096.2 | 242128.656 | 0.04405%
10 | CEILING WORKS | lot | 1 | 818102.004 | 151290 | 74120 | 1043512.004 | 83480.9603 | 83480.9603 | 60523.6962 | 227485.6169 | 1270997.6209 | 1270997.6209 | 0.2312%
11 | PAINTING WORKS | sq.m | 907.38 | 174.6236 | 296.4139 | 0 | 427410 | 34192.8 | 34192.8 | 24789.78 | 93175.38 | 573.7237 | 520585.38 | 0.0947%
12 | DOORS & WINDOWS | sq.m | 108.27 | 2412.4319 | 931.56 | 0 | 362054 | 28964.32 | 28964.32 | 20999.132 | 78927.772 | 4072.9821 | 440981.772 | 0.08022%
13 | FLOOR FINISHES | sq.m | 243.26 | 1120.5418 | 241.8606 | 0 | 331418 | 26513.44 | 26513.44 | 19222.244 | 72249.124 | 1659.4061 | 403667.124 | 0.07343%
14 | RAILINGS | lm | 5.6 | 6002.5 | 2797.5 |  | 49280 | 3942.4 | 3942.4 | 2858.24 | 10743.04 | 10718.4 | 60023.04 | 0.01092%
15 | CARPENTRY WORKS | sq.m | 15.2 | 6075 | 2404.8684 |  | 128894 | 10311.52 | 10311.52 | 7475.852 | 28098.892 | 10328.4797 | 156992.892 | 0.02856%
16 | PHENOLIC PARTITION | sq.m | 17.01 | 2310 | 920.9877 |  | 54959.1 | 4396.728 | 4396.728 | 3187.6278 | 11981.0838 | 3935.343 | 66940.1838 | 0.01218%
17 | PLUMBING WORKS | lot | 1 | 81075 | 25215 | 0 | 106290 | 8503.2 | 8503.2 | 6164.82 | 23171.22 | 129461.22 | 129461.22 | 0.02355%
18 | ELECTRICAL WORKS | lot | 1 | 116967.8795 | 33620 | 0 | 150587.8795 | 12047.0304 | 12047.0304 | 8734.097 | 32828.1577 | 183416.0372 | 183416.0372 | 0.03337%
XX. | CONSTRUCTION OF POLICE SUBSTATION | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | EXCAVATION WORKS | cu.m | 42.105 | 0 | 31.0058 | 71.2504 | 4305.5 | 344.44 | 344.44 | 249.719 | 938.599 | 124.5481 | 5244.099 | 0.000954%
2 | GRAVEL BEDDING | cu.m | 9.6645 | 1150 | 635.7287 | 0 | 17258.175 | 1380.654 | 1380.654 | 1000.9742 | 3762.2822 | 2175.0176 | 21020.4572 | 0.003824%
3 | EARTHFILLING | cu.m | 13.2325 | 632.5 | 928.6227 | 453.4291 | 26657.5563 | 2132.6045 | 2132.6045 | 1546.1383 | 5811.3473 | 2453.7241 | 32468.9035 | 0.005906%
4 | CONCRETE WORKS | cu.m | 12.643 | 5200 | 726.7263 | 237.2855 | 77931.6 | 6234.528 | 6234.528 | 4520.0328 | 16989.0888 | 7507.7663 | 94920.6888 | 0.01727%
5 | REINFORCING STEEL BARS | kgs | 1390.73 | 63 | 5.7437 | 4.3143 | 101603.99 | 8128.3192 | 8128.3192 | 5893.0314 | 22149.6698 | 88.9847 | 123753.6598 | 0.02251%
6 | MASONRY WORKS | sq.m | 78.11 | 579.2044 | 322.814 | 115.2221 | 79456.6547 | 6356.5324 | 6356.5324 | 4608.486 | 17321.5507 | 1238.9989 | 96778.2054 | 0.0176%
7 | PLASTERING WORKS | sq.m | 156.22 | 118.4227 | 161.9383 | 38.4074 | 49798 | 3983.84 | 3983.84 | 2888.284 | 10855.964 | 388.2599 | 60653.964 | 0.01103%
8 | STEEL STRUCTURE | kgs | 3568.08 | 114.5668 | 23.5561 | 20.7731 | 566953.612 | 45356.289 | 45356.289 | 32883.3095 | 123595.8874 | 193.5353 | 690549.4994 | 0.1256%
9 | ROOFING WORKS | sq.m | 77.4 | 900 | 0 |  | 69660 | 5572.8 | 5572.8 | 4040.28 | 15185.88 | 1096.2 | 84845.88 | 0.01543%
10 | CEILING WORKS | lot | 1 | 174690.9798 | 33620 | 6000 | 214310.9798 | 17144.8784 | 17144.8784 | 12430.0368 | 46719.7936 | 261030.7734 | 261030.7734 | 0.04748%
11 | PAINTING WORKS | sq.m | 257.02 | 176.64 | 294.3156 | 0 | 121045 | 9683.6 | 9683.6 | 7020.61 | 26387.81 | 573.6239 | 147432.81 | 0.02682%
12 | DOORS & WINDOWS | sq.m | 26.78 | 3314.7125 | 1255.4145 | 0 | 122388 | 9791.04 | 9791.04 | 7098.504 | 26680.584 | 5566.4146 | 149068.584 | 0.02712%
13 | FLOOR FINISHES | sq.m | 57.52 | 1274.0612 | 255.3547 | 0 | 87972 | 7037.76 | 7037.76 | 5102.376 | 19177.896 | 1862.8285 | 107149.896 | 0.01949%
14 | PLUMBING WORKS | lot | 1 | 44660 | 13210 | 0 | 57870 | 4629.6 | 4629.6 | 3356.46 | 12615.66 | 70485.66 | 70485.66 | 0.01282%
15 | ELECTRICAL WORKS | lot | 1 | 26045.8976 | 8405 | 0 | 34450.8976 | 2756.0718 | 2756.0718 | 1998.1521 | 7510.2957 | 41961.1933 | 41961.1933 | 0.007633%
XXI. | CONSTRUCTION OF SUBSTATION / POWERHOUSE | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | CONSTRUCTION OF SUBSTATION / POWERHOUSE | lot | 1 | 147906.3333 | 29376 | 48000 | 225282.3333 | 18022.5867 | 18022.5867 | 13066.3753 | 49111.5487 | 274393.882 | 274393.882 | 0.04992%
XXII. | FURNITURES | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | PUBLIC OFFICES | lot | 1 | 14617430 | 0 | 0 | 14617430 | 1169394.4 | 1169394.4 | 847810.94 | 3186599.74 | 17804029.74 | 17804029.74 | 3.239%
2 | OFFICE OF THE MUNICIPAL MAYOR | lot | 1 | 631772 | 0 | 0 | 631772 | 50541.76 | 50541.76 | 36642.776 | 137726.296 | 769498.296 | 769498.296 | 0.14%
3 | OFFICE OF THE MUNICIPAL VICE MAYOR | lot | 1 | 143370 | 0 | 0 | 143370 | 11469.6 | 11469.6 | 8315.46 | 31254.66 | 174624.66 | 174624.66 | 0.03177%
4 | AUDIO VISUAL ROOM | lot | 1 | 708000 | 0 | 0 | 708000 | 56640 | 56640 | 41064 | 154344 | 862344 | 862344 | 0.1569%
5 | ATRIUM & LOBBY FURNITURES | lot | 1 | 1178248.88 | 0 | 0 | 1178248.88 | 94259.9104 | 94259.9104 | 68338.435 | 256858.2558 | 1435107.1358 | 1435107.1358 | 0.2611%
XXIII. | EMERGENCY STANDBY GENERATOR | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | EMERGENCY STANDBY GENERATOR | lot | 1 | 5087760 | 0 | 0 | 5087760 | 407020.8 | 407020.8 | 295090.08 | 1109131.68 | 6196891.68 | 6196891.68 | 1.127%
XXIV. | DESIGN PHASE | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
1 | DESIGN PHASE | lot | 1 | 12847534.8522 | 0 | 0 | 12847534.8522 | 1027802.7882 | 1027802.7882 | 745157.0214 | 2800762.5978 | 15648297.45 | 15648297.45 | 2.847%
GRAND TOTAL | [6 empty] | 451331350.0579 | 36106508.0046 | 36106508.0046 | 26177218.3034 | 98390234.3126 |  | 549721584.3706 | 100%