## Accomplishment Report
Item No. | Description of Work | Unit/s | Qty | Unit Cost | Total Cost | Weighted % | Qty | Unit/s | Total | PREVIOUS | THIS PERIOD | ACCOMPLISHMEN TO DATE | % | Remarks
I | GENERAL REQUIREMENTS | [7 empty] | 0 |  | 0 | 0
| PERMITS, FEES, TAXES AND LICENSES | [7 empty] | 0 |  | 0 | 0
| a. Barangay Permits | [7 empty] | 0 |  | 0 | 0
| b. Local Government Permits | [7 empty] | 0 |  | 0 | 0
| c. BFD Permits | [7 empty] | 0 |  | 0 | 0
| d. DENR Permits | [7 empty] | 0 |  | 0 | 0
0
| INSURANCES AND BONDS | [5 empty] | 0
| a. Guarantee / Warranty Bonds | [7 empty] | 0 |  | 0 | 0
| b. Contractor's All Risk Insurance (CARI) | [7 empty] | 0 |  | 0 | 0
| c. Performance Bond | [7 empty] | 0 |  | 0 | 0
| d. Other Insurances and Bonds | [7 empty] | 0 |  | 0 | 0
| Mobilization and Demobilization | lot | 1 | 103229 | 103229 | 0.0023947 |  | lot | 0 | 103229 | 0 | 103229 | 0.0023947 | Completed
| Site Management Work | [7 empty] | 0 |  | 0 | 0
| a. Project Management | lot | 1 | 678976 | 678976 | 0.015751 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| b. Admin Support - Accounting, Procurement, Logistics | lot | 1 | 279580 | 279580 | 0.0064858 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| c.Quality Management | lot | 1 | 279580 | 279580 | 0.0064858 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| d. Engineering Management - Clarifications & Drawings | lot | 1 | 319519 | 319519 | 0.0074123 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Temporary Works | [7 empty] | 0 |  | 0 | 0
| a. Site Office | [7 empty] | 0 |  | 0 | 0
| b. Warehouse | lot | 1 | 51615 | 51615 | 0.0011974 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| b. Site Office Materials & Communication | lot | 1 | 14747 | 14747 | 0.0003421 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| c. Temporary Tools & Cleaning Materials | lot | 1 | 7374 | 7374 | 0.00017106 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| b. Off-site Barracks - Construction and-or Rent - Electric Consumption - Water Consumption | lot | 1 | 184338 | 184338 | 0.0042763 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Temporary Utilities | [7 empty] | 0 | 0 | 0 | 0 | 0
| a. On-Site Water Consumption | [7 empty] | 0 |  | 0 | 0
| b. On-Site Electric Consumption | [7 empty] | 0 |  | 0 | 0
| Security, Safety and Protection | [7 empty] | 0 | 0 | 0 | 0 | 0
| a. Safety Officer | lot | 1 | 331807 | 331807 | 0.0076973 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| b. Personal Protective Equipment (PPE's) | lot | 1 | 73735 | 73735 | 0.0017105 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| b. Security Guards | lot | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0
| Quality Standard and Control | [7 empty] | 0 |  | 0 | 0
| a. Shopdrawings, As-built plans for Occupancy including Sign & Seal | lot | 1 | 117976 | 117976 | 0.0027368 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| b. Material Testing | [7 empty] | 0 |  | 0 | 0
| Transportation | [7 empty] | 0 | 0 | 0 | 0 | 0
| a. Manpower Service | lot | 1 | 147470 | 147470 | 0.003421 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| b. Engineer Transportation | lot | 1 | 110603 | 110603 | 0.0025658 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| c. Village Delivery/Gate Pass Fees | [7 empty] | 0 | 0 | 0 | 0 | 0
III | MECHANICAL WORKS | [7 empty] | 0 |  | 0 | 0
| Mechanical Works | [7 empty] | 0 |  | 0 | 0
I-A. | AIR CONDITIONING- VRV SYSTEM A | [7 empty] | 0 |  | 0 | 0
| ACCU- 18HP Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 0.051574 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF A (OR No. 2, PNCOU, OR No.3, OR, Pantry, OR Complex Conference Room) Model: FXAQ50BVM | units | 6 | 55087.34 | 330524.04 | 0.0076676 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF A (OR No. 2 ENT, OR No. 1 ENT, Chief Nurse, OR Pharmacy) Model: FXAQ63BVM | units | 3 | 56222.86 | 168668.58 | 0.0039128 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF A (Corridor Near OR No.1, Corridor Near OR No. 2 ENT) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.0040611 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Accessories: | [7 empty] | 0 | 0 | 0 | 0 | 0
| Navigation Wired Controller Model: BRC1E63 | units | 11 | 11760.72 | 129367.92 | 0.0030011 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.0010367 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A22T | units | 2 | 4351.47 | 8702.94 | 0.00020189 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 2 | 4939.51 | 9879.02 | 0.00022918 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A732T | units | 3 | 8232.51 | 24697.53 | 0.00057294 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A733T | units | 3 | 14112.87 | 42338.61 | 0.00098218 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.00041743 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [7 empty] | 0 | 0 | 0 | 0 | 0
| 1/4" | length/s | 10 | 2120.33 | 21203.3 | 0.00049188 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 13 | 2952.35 | 38380.55 | 0.00089036 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 14 | 4696.92 | 65756.88 | 0.0015254 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 9 | 6775.95 | 60983.55 | 0.0014147 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 9 | 8642.33 | 77780.97 | 0.0018044 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 10870.01 | 21740.02 | 0.00050433 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 8 | 15566.92 | 124535.36 | 0.002889 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 5 | 21015.33 | 105076.65 | 0.0024376 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 4 | 21015.33 | 84061.32 | 0.0019501 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes Insulation 25mm Thick | [7 empty] | 0 |  | 0 | 0
| 1/4" | length/s | 19 | 433.57 | 8237.83 | 0.0001911 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 26 | 441.83 | 11487.58 | 0.00026649 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 27 | 516.15 | 13936.05 | 0.00032329 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 18 | 629.71 | 11334.78 | 0.00026295 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 17 | 708.16 | 12038.72 | 0.00027928 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 4 | 784.55 | 3138.2 | 7.2801e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 15 | 846.49 | 12697.35 | 0.00029456 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 10 | 896.03 | 8960.3 | 0.00020786 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 8 | 896.03 | 7168.24 | 0.00016629 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 57975.92 | 57975.92 | 0.0013449 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 22 | 3207.48 | 70564.56 | 0.001637 |  | pc/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 22281.85 | 22281.85 | 0.0005169 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes | [7 empty] | 0 | 0 | 0 | 0 | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 39 | 404.15 | 15761.85 | 0.00036565 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 22 | 641.83 | 14120.26 | 0.00032757 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes Rubber Insulation 1.5 meters | [7 empty] | 0 |  | 0 | 0
| 3/4'' thick for 32mm pvc | length/s | 77 | 427.67 | 32930.59 | 0.00076393 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 43 | 812.57 | 34940.51 | 0.00081056 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Drain Pump | [7 empty] | 0 | 0 | 0 | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 9 | 30473.16 | 274258.44 | 0.0063623 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
[9 empty] | 0 | 0 | 0 | 0 | 0
| Fittings | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wye Reducer 50 x 32 | pcs | 11 | 192.46 | 2117.06 | 4.9112e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Tee 32mm | pcs | 2 | 53.47 | 106.94 | 2.4808e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Tee Reducer 50 x 32 | pcs | 2 | 203.15 | 406.3 | 9.4255e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Elbow 32mm | pcs | 6 | 43.63 | 261.78 | 6.0728e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cleanout 50mm | pcs | 4 | 213.84 | 855.36 | 1.9843e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [7 empty] | 0 | 0 | 0 | 0 | 0
| Rough-ins | [7 empty] | 0 | 0 | 0 | 0 | 0
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.0007313 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit 20mm | m | 586 | 65.87 | 38599.82 | 0.00089545 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 29 | 32.09 | 930.61 | 2.1589e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cables / Wires | [7 empty] | 0 | 0 | 0 | 0 | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 419 | 80.84 | 33871.96 | 0.00078577 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 71 | 78.48 | 5572.08 | 0.00012926 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 7.2445e-05 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 790.33 | 46629.47 | 0.0010817 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| for ground: | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 72 | 78.48 | 5650.56 | 0.00013108 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 8.717e-05 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
I-B. | CONSUMABLES | [7 empty] | 0 |  | 0 | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Rugby | bottle | 21 | 277.99 | 5837.79 | 0.00013543 |  | bottle | 0 | 0 | 0 | 0 | 0 | Ongoing
| White Tape | rolls | 42 | 374.22 | 15717.24 | 0.00036461 |  | rolls | 0 | 0 | 0 | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 94 | 171.07 | 16080.58 | 0.00037304 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 | 0 | 0 | 0 | Ongoing
| Loop Hangers | pcs | 351 | 42.78 | 15015.78 | 0.00034834 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Freon | tank | 6 | 14497.77 | 86986.62 | 0.0020179 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nitrogen | tank | 3 | 18175.66 | 54526.98 | 0.0012649 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Mapp Gas | tank | 11 | 855.33 | 9408.63 | 0.00021826 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Silver Rod | pcs | 141 | 53.47 | 7539.27 | 0.0001749 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
I-C. | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
I-D. | MISCELLANEOUS | lot | 1 | 5684.06 | 5684.06 | 0.00013186 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
I-E. | TESTING & COMMISSIONING | lot | 1 | 41291.54 | 41291.54 | 0.00095789 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
II.A | AIR CONDITIONING- VRV SYSTEM B | [7 empty] | 0 | 0 | 0 | 0 | 0
| ACCU- Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 0.051574 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF B (OR No. 1 and 3, OR No. 1 Miyake Eye (2), OR No. 2 NSS(2), OR No. 3 Euro-open (2), OR No. 8 Ortho, NSS/ Pay, Storage Room, OR Complex Conference Room) Model: FXAQ50BVM | units | 10 | 55087.34 | 550873.4 | 0.012779 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF B ( OR no. 4, 6, 13, 14, 15, OR Pharmacy) Model: FXAQ63BVM | units | 2 | 56222.86 | 112445.72 | 0.0026085 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF B (Corridor near OR No. 2 NSS, Corridor Near Supply Room) Model: FXFQ140AVM | units | 1 | 87530.69 | 87530.69 | 0.0020306 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Accessories: | [7 empty] | 0 |  | 0 | 0
| Wired Remote Controller Model: BRC1E63 | units | 13 | 11760.72 | 152889.36 | 0.0035468 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 1 | 22345.37 | 22345.37 | 0.00051837 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A22T | units | 6 | 4351.47 | 26108.82 | 0.00060568 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 1 | 4939.51 | 4939.51 | 0.00011459 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A72T | units | 3 | 8232.51 | 24697.53 | 0.00057294 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A73T | units | 2 | 14112.87 | 28225.74 | 0.00065479 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 2 | 5997.97 | 11995.94 | 0.00027828 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [7 empty] | 0 | 0 | 0 | 0 | 0
| 1/4" | length/s | 14 | 2120.33 | 29684.62 | 0.00068863 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 11 | 2952.35 | 32475.85 | 0.00075338 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 15 | 4696.92 | 70453.8 | 0.0016344 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 12 | 6775.95 | 81311.4 | 0.0018863 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 13 | 8642.33 | 112350.29 | 0.0026063 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 1 | 10870.01 | 10870.01 | 0.00025217 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.0018056 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 1 | 27039.77 | 27039.77 | 0.00062728 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 12 | 27039.77 | 324477.24 | 0.0075273 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes Insulation 25mm Thick | [7 empty] | 0 | 0 | 0 | 0 | 0
| 1/4" | length/s | 27 | 433.57 | 11706.39 | 0.00027157 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 21 | 441.83 | 9278.43 | 0.00021524 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 30 | 516.15 | 15484.5 | 0.00035921 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 24 | 629.71 | 15113.04 | 0.0003506 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 26 | 708.16 | 18412.16 | 0.00042713 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 784.55 | 1569.1 | 3.64e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 9 | 846.49 | 7618.41 | 0.00017673 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 2 | 1011.66 | 2023.32 | 4.6938e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 24 | 1011.66 | 24279.84 | 0.00056325 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 87733.46 | 87733.46 | 0.0020353 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 26 | 3207.48 | 83394.48 | 0.0019346 |  | pc/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 8234.77 | 8234.77 | 0.00019103 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes | [7 empty] | 0 |  | 0 | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 37 | 404.15 | 14953.55 | 0.0003469 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 24 | 641.83 | 15403.92 | 0.00035734 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes Rubber Insulation 1.5 meters | [7 empty] | 0 |  | 0 | 0
| 3/4'' thick for 32mm pvc | length/s | 74 | 427.67 | 31647.58 | 0.00073417 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 48 | 812.57 | 39003.36 | 0.00090481 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Drain Pump | [7 empty] | 0 | 0 | 0 | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 12 | 30473.16 | 365677.92 | 0.0084831 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Fittings | [7 empty] | 0 |  | 0 | 0
| Wye 50mm | pcs | 3 | 213.84 | 641.52 | 1.4882e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wye Reducer 50 x 32 | pcs | 13 | 192.46 | 2501.98 | 5.8042e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Tee 32mm | pcs | 3 | 53.47 | 160.41 | 3.7212e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Elbow 32mm | pcs | 6 | 43.63 | 261.78 | 6.0728e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cleanout 50mm | pcs | 4 | 213.84 | 855.36 | 1.9843e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [7 empty] | 0 | 0 | 0 | 0 | 0
| Rough-ins | [7 empty] | 0 | 0 | 0 | 0 | 0
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.0007313 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit | m | 673 | 65.87 | 44330.51 | 0.0010284 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 34 | 32.09 | 1091.06 | 2.5311e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cables / Wires | [7 empty] | 0 |  | 0 | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 482 | 80.84 | 38964.88 | 0.00090392 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 94 | 78.48 | 7377.12 | 0.00017114 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 13 | 115.83 | 1505.79 | 3.4932e-05 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 789.47 | 46578.73 | 0.0010805 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| for ground: | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 85 | 78.48 | 6670.8 | 0.00015475 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 8.717e-05 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
II.B | CONSUMABLES | [7 empty] | 0 | 0 | 0 | 0 | 0
| Vibration Isolator | pcs | 16 | 1389.91 | 22238.56 | 0.0005159 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 6 | 2523.22 | 15139.32 | 0.00035121 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Rugby | bottle | 25 | 277.99 | 6949.75 | 0.00016122 |  | bottle | 0 | 0 | 0 | 0 | 0 | Ongoing
| White Tape | rolls | 49 | 374.22 | 18336.78 | 0.00042538 |  | rolls | 0 | 0 | 0 | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 107 | 171.07 | 18304.49 | 0.00042463 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 | 0 | 0 | 0 | Ongoing
| Loop Hangers | pcs | 402 | 42.78 | 17197.56 | 0.00039895 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Freon | tank | 7 | 14497.77 | 101484.39 | 0.0023543 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.0016866 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Mapp Gas | tank | 12 | 855.33 | 10263.96 | 0.00023811 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Silver Rod | pcs | 160 | 53.47 | 8555.2 | 0.00019847 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
II.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
II.D | MISCELLANEOUS | lot | 1 | 6640.71 | 6640.71 | 0.00015405 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
II.E | TESTING & COMMISIONING | lot | 1 | 47190.33 | 47190.33 | 0.0010947 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
III.A | AIR CONDITIONING- VRV SYSTEM C | [7 empty] | 0 | 0 | 0 | 0 | 0
| ACCU- Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 0.051574 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF C (Storage Room, OR No. 8 Ortho, NSS/Pay, OR No. 9 Plastic Surgery (2) ) Model: FXAQ50BVM | units | 1 | 55087.34 | 55087.34 | 0.0012779 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF C (OR No. 4, Euro- Endo (2), OR No. 7 Ortho, OR. 12 Pedia, OR No. 10 Pay) Model: FXAQ63BVM | units | 7 | 56222.86 | 393560.02 | 0.0091299 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF C (Corridor near Ortho, Corridor near OR. No. 10, Corridor near NSS/Pay) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.0040611 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Accessories: | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wired Remote Controller Model: BRC1E63 | units | 10 | 11760.72 | 117607.2 | 0.0027283 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.0010367 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 2 | 4939.51 | 9879.02 | 0.00022918 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A72T | units | 4 | 8232.51 | 32930.04 | 0.00076392 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A73T | units | 3 | 14112.87 | 42338.61 | 0.00098218 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.00041743 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [7 empty] | 0 | 0 | 0 | 0 | 0
| 1/4" | length/s | 1 | 2120.33 | 2120.33 | 4.9188e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 11 | 2952.35 | 32475.85 | 0.00075338 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 2 | 4696.92 | 9393.84 | 0.00021792 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 14 | 6775.95 | 94863.3 | 0.0022007 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 9 | 8642.33 | 77780.97 | 0.0018044 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 1 | 10870.01 | 10870.01 | 0.00025217 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.0018056 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 3 | 21015.33 | 63045.99 | 0.0014626 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 7 | 27039.77 | 189278.39 | 0.0043909 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes Insulation 25mm Thick | [7 empty] | 0 |  | 0 | 0
| 1/4" | length/s | 2 | 433.57 | 867.14 | 2.0116e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 21 | 441.83 | 9278.43 | 0.00021524 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 4 | 516.15 | 2064.6 | 4.7895e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 27 | 629.71 | 17002.17 | 0.00039442 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 17 | 708.16 | 12038.72 | 0.00027928 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 784.55 | 1569.1 | 3.64e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 10 | 846.49 | 8464.9 | 0.00019637 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 5 | 896.03 | 4480.15 | 0.00010393 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 13 | 1011.66 | 13151.58 | 0.00030509 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 59135.15 | 59135.15 | 0.0013718 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 20 | 3207.48 | 64149.6 | 0.0014882 |  | pc/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 19711.72 | 19711.72 | 0.00045728 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes | [7 empty] | 0 | 0 | 0 | 0 | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 33 | 404.15 | 13336.95 | 0.00030939 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 12 | 641.83 | 7701.96 | 0.00017867 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes Rubber Insulation 1.5 meters | [7 empty] | 0 | 0 | 0 | 0 | 0
| 3/4'' thick for 32mm pvc | length/s | 66 | 427.67 | 28226.22 | 0.0006548 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 23 | 812.57 | 18689.11 | 0.00043355 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Drain Pump | [7 empty] | 0 | 0 | 0 | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 11 | 30473.16 | 335204.76 | 0.0077762 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Fittings | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wye Reducer 50 x 32 | length/s | 7 | 192.46 | 1347.22 | 3.1253e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Tee 32mm | length/s | 6 | 53.47 | 320.82 | 7.4425e-06 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Elbow 32mm | length/s | 7 | 43.63 | 305.41 | 7.085e-06 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cleanout 50mm | length/s | 2 | 213.84 | 427.68 | 9.9214e-06 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [7 empty] | 0 | 0 | 0 | 0 | 0
| Rough-ins | [7 empty] | 0 |  | 0 | 0
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.0007313 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit 20mm | m | 444 | 65.87 | 29246.28 | 0.00067846 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 26 | 32.09 | 834.34 | 1.9355e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cables / Wires | [7 empty] | 0 |  | 0 | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 291 | 80.84 | 23524.44 | 0.00054573 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 63 | 78.49 | 4944.87 | 0.00011471 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 7.2445e-05 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 789.47 | 46578.73 | 0.0010805 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| for ground: | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 65 | 78.49 | 5101.85 | 0.00011835 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 8.717e-05 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
III.B | CONSUMABLES | [7 empty] | 0 |  | 0 | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Rugby | bottle | 15 | 277.99 | 4169.85 | 9.6733e-05 |  | bottle | 0 | 0 | 0 | 0 | 0 | Ongoing
| White Tape | rolls | 30 | 374.22 | 11226.6 | 0.00026044 |  | rolls | 0 | 0 | 0 | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 65 | 171.07 | 11119.55 | 0.00025795 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 | 0 | 0 | 0 | Ongoing
| Loop Hangers | pcs | 244 | 42.78 | 10438.32 | 0.00024215 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Freon | tank | 5 | 14497.77 | 72488.85 | 0.0016816 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nitrogen | tank | 3 | 18175.66 | 54526.98 | 0.0012649 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Mapp Gas | tank | 8 | 812.57 | 6500.56 | 0.0001508 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Silver Rod | pcs | 98 | 53.47 | 5240.06 | 0.00012156 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
III.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
III.D | MISCELLANEOUS | lot | 1 | 5010.49 | 5010.49 | 0.00011623 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
III.E | TESTING & COMMISSIONING | lot | 1 | 38342.14 | 38342.14 | 0.00088947 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
IV.A | AIR CONDITIONING- VRV SYSTEM D | [7 empty] | 0 | 0 | 0 | 0 | 0
| ACCU- Model: RXQ20BYM | units | 3 | 789317.19 | 2367951.57 | 0.054932 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF C (Storage Room, OR No. 8 Ortho, NSS/Pay, OR No. 9 Plastic Surgery (2) ) Model: FXAQ50BVM | units | 6 | 55087.34 | 330524.04 | 0.0076676 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF C (OR No. 4, Euro- Endo (2), OR No. 7 Ortho, OR. 12 Pedia, OR No. 10 Pay) Model: FXAQ63BVM | units | 4 | 56222.86 | 224891.44 | 0.0052171 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF C (Corridor near Ortho, Corridor near OR. No. 10, Corridor near NSS/Pay) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.0040611 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Accessories: | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wired Remote Controller Model: BRC1E63 | units | 12 | 11760.72 | 141128.64 | 0.0032739 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.0010367 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A22T | units | 4 | 4351.47 | 17405.88 | 0.00040379 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 1 | 4939.51 | 4939.51 | 0.00011459 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A72T | units | 3 | 8232.51 | 24697.53 | 0.00057294 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A73T | units | 3 | 14112.87 | 42338.61 | 0.00098218 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.00041743 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [7 empty] | 0 | 0 | 0 | 0 | 0
| 1/4" | length/s | 8 | 2120.33 | 16962.64 | 0.0003935 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 12 | 2952.35 | 35428.2 | 0.00082187 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 10 | 4696.92 | 46969.2 | 0.0010896 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 14 | 6775.95 | 94863.3 | 0.0022007 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 16 | 8642.33 | 138277.28 | 0.0032078 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 10870.01 | 21740.02 | 0.00050433 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.0018056 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 2 | 21015.33 | 42030.66 | 0.00097504 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 14 | 27039.77 | 378556.78 | 0.0087819 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipes Insulation 25mm Thick | [7 empty] | 0 | 0 | 0 | 0 | 0
| 1/4" | length/s | 16 | 433.57 | 6937.12 | 0.00016093 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/8" | length/s | 24 | 441.83 | 10603.92 | 0.00024599 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1/2" | length/s | 19 | 516.15 | 9806.85 | 0.0002275 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5/8" | length/s | 27 | 629.71 | 17002.17 | 0.00039442 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4" | length/s | 31 | 708.16 | 21952.96 | 0.00050927 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 7/8" | length/s | 4 | 784.55 | 3138.2 | 7.2801e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-1/8" | length/s | 10 | 846.49 | 8464.9 | 0.00019637 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-3/8" | length/s | 4 | 896.03 | 3584.12 | 8.3145e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 1-5/8" | length/s | 27 | 1011.66 | 27314.82 | 0.00063366 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 96659.97 | 96659.97 | 0.0022423 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 24 | 3207.48 | 76979.52 | 0.0017858 |  | pc/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 32220 | 32220 | 0.00074745 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes | [7 empty] | 0 |  | 0 | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 31 | 404.15 | 12528.65 | 0.00029064 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 38 | 641.83 | 24389.54 | 0.00056579 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Condensate Drain Pipes Rubber Insulation 1.5 meters | [7 empty] | 0 | 0 | 0 | 0 | 0
| 3/4'' thick for 32mm pvc | length/s | 61 | 427.67 | 26087.87 | 0.00060519 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 75 | 812.57 | 60942.75 | 0.0014138 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Drain Pump | [7 empty] | 0 |  | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 10 | 30473.16 | 304731.6 | 0.0070692 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Fittings | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wye 50mm | length/s | 2 | 213.84 | 427.68 | 9.9214e-06 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wye Reducer 50 x 32 | length/s | 11 | 192.46 | 2117.06 | 4.9112e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Tee 32mm | length/s | 3 | 53.47 | 160.41 | 3.7212e-06 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Tee Reducer 50 x 32 | length/s | 3 | 203.15 | 609.45 | 1.4138e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Elbow 32mm | length/s | 7 | 43.63 | 305.41 | 7.085e-06 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cleanout 50mm | length/s | 6 | 213.84 | 1283.04 | 2.9764e-05 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [7 empty] | 0 |  | 0 | 0
| Rough-ins | [7 empty] | 0 | 0 | 0 | 0 | 0
| liquid-tight metallic flexible conduits 2" | m | 78 | 763.39 | 59544.42 | 0.0013813 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit 20mm | m | 654 | 65.87 | 43078.98 | 0.00099936 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 32 | 32.09 | 1026.88 | 2.3822e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Cables / Wires | [7 empty] | 0 | 0 | 0 | 0 | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 472 | 80.84 | 38156.48 | 0.00088516 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 78 | 77.05 | 6009.9 | 0.00013942 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 7.2445e-05 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 38.0mm² THHN (5 meters per Unit) | m | 59 | 938.2 | 55353.8 | 0.0012841 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| for ground: | [7 empty] | 0 | 0 | 0 | 0 | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 78 | 75.36 | 5878.08 | 0.00013636 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire 14.0mm² THHN (G) (5 meters per Unit) | m | 20 | 311.01 | 6220.2 | 0.0001443 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
IV.B | CONSUMABLES | [7 empty] | 0 | 0 | 0 | 0 | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Rugby | bottle | 24 | 277.99 | 6671.76 | 0.00015477 |  | bottle | 0 | 0 | 0 | 0 | 0 | Ongoing
| White Tape | rolls | 47 | 374.22 | 17588.34 | 0.00040802 |  | rolls | 0 | 0 | 0 | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 104 | 171.07 | 17791.28 | 0.00041273 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 | 0 | 0 | 0 | Ongoing
| Loop Hangers | pcs | 393 | 42.78 | 16812.54 | 0.00039002 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Freon | tank | 8 | 14497.77 | 115982.16 | 0.0026906 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.0016866 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Mapp Gas | tank | 12 | 812.57 | 9750.84 | 0.0002262 |  | tank | 0 | 0 | 0 | 0 | 0 | Ongoing
| Silver Rod | pcs | 158 | 53.47 | 8448.26 | 0.00019598 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 | 0 | 0 | 0 | Ongoing
IV.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
IV.D | MISCELLANEOUS | lot | 1 | 7277.91 | 7277.91 | 0.00016883 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
IV.E | TESTING & COMMISSIONING | lot | 1 | 44240.94 | 44240.94 | 0.0010263 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
IV | ELECTRICAL WORKS | [7 empty] | 0 | 0 | 0 | 0 | 0
| Electrical Works | [7 empty] | 0 | 0 | 0 | 0 | 0
I. | Service Entrance | [7 empty] | 0 | 0 | 0 | 0 | 0
II. | Feeder | [7 empty] | 0 | 0 | 0 | 0 | 0
| Feeder Wire | [7 empty] | 0 | 0 | 0 | 0 | 0
| 250mm² THHN | m | 726 | 7092.36 | 5149053.36 | 0.11945 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| 200mm² THHN | m | 117 | 5509.16 | 644571.72 | 0.014953 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| 38mm² THHN | m | 390 | 1126.48 | 439327.2 | 0.010192 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| for ground: | [7 empty] | 0 | 0 | 0 | 0 | 0
| 80mm² THHN | m | 242 | 2129.76 | 515401.92 | 0.011956 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| 30mm² THHN | m | 39 | 823.69 | 32123.91 | 0.00074522 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| 14mm² THHN | m | 130 | 358.87 | 46653.1 | 0.0010823 |  | m | 0 | 0 | 0 | 0 | 0 | Ongoing
| Roughing-ins | [7 empty] | 0 | 0 | 0 | 0 | 0
| 90mm dia. IMC | length/s | 94 | 9301.67 | 874356.98 | 0.020284 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 40mm dia. IMC | length/s | 45 | 2672.9 | 120280.5 | 0.0027903 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
III. | Panel Board & Pullbox | [7 empty] | 0 | 0 | 0 | 0 | 0
| DP-Main | Assy | 1 | 772225.45 | 772225.45 | 0.017914 |  | Assy | 0 | 0 | 0 | 0 | 0 | Ongoing
| Main CB: 1200AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 1 - 700AT, 3P | [7 empty] | 0 |  | 0 | 0
| 4 - 125AT, 3P | [7 empty] | 0 | 0 | 0 | 0 | 0
| PP-System A | Assy | 1 | 125827.11 | 125827.11 | 0.002919 |  | Assy | 0 | 0 | 0 | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 | 0 | 0 | 0 | 0
| Branches: 2 - 40AT, 3P | [7 empty] | 0 | 0 | 0 | 0 | 0
| 3 - 40AT, 2P | [7 empty] | 0 | 0 | 0 | 0 | 0
| 9 - 30AT, 2P | [7 empty] | 0 | 0 | 0 | 0 | 0
| PP-System B | Assy | 1 | 135268.13 | 135268.13 | 0.003138 |  | Assy | 0 | 0 | 0 | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 | 0 | 0 | 0 | 0
| Branches: 1 - 40AT, 3P | [7 empty] | 0 | 0 | 0 | 0 | 0
| 2 - 40AT, 2P | [7 empty] | 0 |  | 0 | 0
| 11 - 30AT, 2P | [7 empty] | 0 | 0 | 0 | 0 | 0
| PP-System C | Assy | 1 | 120190.82 | 120190.82 | 0.0027882 |  | Assy | 0 | 0 | 0 | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 | 0 | 0 | 0 | 0
| Branches: 2 - 40AT, 3P | [7 empty] | 0 |  | 0 | 0
| 7 - 40AT, 2P | [7 empty] | 0 | 0 | 0 | 0 | 0
| 5 - 30AT, 2P | [7 empty] | 0 |  | 0 | 0
| PP-System D | Assy | 1 | 131472.25 | 131472.25 | 0.0030499 |  | Assy | 0 | 0 | 0 | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 3 - 40AT, 3P | [7 empty] | 0 |  | 0 | 0
| 4 - 40AT, 2P | [7 empty] | 0 | 0 | 0 | 0 | 0
| 8 - 30AT, 2P | [7 empty] | 0 | 0 | 0 | 0 | 0
| PP-Outdoor | Assy | 1 | 473575.57 | 473575.57 | 0.010986 |  | Assy | 0 | 0 | 0 | 0 | 0 | Ongoing
| Main CB: 700AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 4 - 150AT, 3P | [7 empty] | 0 | 0 | 0 | 0 | 0
| Transformer | Assy | 1 | 932598.82 | 932598.82 | 0.021635 |  | Assy | 0 | 0 | 0 | 0 | 0 | Ongoing
| 500KVA Step Down Dry Type Transformer, 480V to 230V, 3P Floor mounted, Indoor Type, 60Hz, Nema1 "TRANSPHIL" | [7 empty] | 0 |  | 0 | 0
| ECB 1250AT Nema 12 | pc | 1 | 302047.59 | 302047.59 | 0.007007 |  | pc | 0 | 0 | 0 | 0 | 0 | Ongoing
| Pullbox (350mm x 350mm x 200mm) | pc | 5 | 5538.24 | 27691.2 | 0.00064239 |  | pc | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wire Gutter | lot | 1 | 32074.68 | 32074.68 | 0.00074408 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
IV. | Mechanical System Power Supply | [7 empty] | 0 |  | 0 | 0
| ECB's | [7 empty] | 0 | 0 | 0 | 0 | 0
| ECB 150AT, 3P, 230V, Nema3R | pc | 4 | 29019.11 | 116076.44 | 0.0026928 |  | pc | 0 | 0 | 0 | 0 | 0 | Ongoing
| ECB 40AT, 3P, 230V, Nema3R | pc | 7 | 11083.84 | 77586.88 | 0.0017999 |  | pc | 0 | 0 | 0 | 0 | 0 | Ongoing
| ECB 40AT, 2P, 230V, Nema3R | pc | 16 | 9429.22 | 150867.52 | 0.0034999 |  | pc | 0 | 0 | 0 | 0 | 0 | Ongoing
| ECB 30AT, 2P, 230V, Nema3R | pc | 23 | 9429.22 | 216872.06 | 0.0050311 |  | pc | 0 | 0 | 0 | 0 | 0 | Ongoing
| Roughing-ins | [7 empty] | 0 | 0 | 0 | 0 | 0
| 40mm dia. IMC | length/s | 49 | 2672.9 | 130972.1 | 0.0030383 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 25mm dia. IMC | length/s | 1003 | 1753.43 | 1758690.29 | 0.040799 |  | length/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Boxes | [7 empty] | 0 |  | 0 | 0
| Junction boxes with cover | pc/s | 195 | 125.85 | 24540.75 | 0.0005693 |  | pc/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| Wires | [7 empty] | 0 | 0 | 0 | 0 | 0
| 50mm² THHN | Lm/s | 429 | 1395.9 | 598841.1 | 0.013892 |  | Lm/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 6798 | 144.13 | 979795.74 | 0.02273 |  | Lm/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| for ground: | [7 empty] | 0 | 0 | 0 | 0 | 0
| 14mm² THHN | Lm/s | 143 | 358.87 | 51318.41 | 0.0011905 |  | Lm/s | 0 | 0 | 0 | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 3185 | 144.13 | 459054.05 | 0.010649 |  | Lm/s | 0 | 0 | 0 | 0 | 0 | Ongoing
V. | Chipping & Restoration Works (Rough only) | lot | 1 | 145441.09 | 145441.09 | 0.003374 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
VI. | Hangers & Supports | lot | 1 | 174529.31 | 174529.31 | 0.0040488 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
VII. | Miscelleneuos | lot | 1 | 87264.66 | 87264.66 | 0.0020244 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
VIII. | Testing & Commissioning | lot | 1 | 884818.61 | 884818.61 | 0.020526 |  | lot | 0 | 0 | 0 | 0 | 0 | Ongoing
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | Ongoing
IV.B | CONSUMABLES | [7 empty] | 0 |  | 0 | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 | 0 | 0 | 0
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 | 0 | 0 | 0
| Rugby | bottle | 24 | 277.99 | 6671.76 | 0.00015477 |  | bottle | 0 | 0 | 0 | 0 | 0
| White Tape | rolls | 47 | 374.22 | 17588.34 | 0.00040802 |  | rolls | 0 | 0 | 0 | 0 | 0
| Threaded rod 3/8 (6 meters) | length/s | 104 | 171.07 | 17791.28 | 0.00041273 |  | length/s | 0 | 0 | 0 | 0 | 0
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 | 0 | 0 | 0
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 | 0 | 0 | 0
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 | 0 | 0 | 0
| Loop Hangers | pcs | 393 | 42.78 | 16812.54 | 0.00039002 |  | pcs | 0 | 0 | 0 | 0 | 0
| Freon | tank | 8 | 14497.77 | 115982.16 | 0.0026906 |  | tank | 0 | 0 | 0 | 0 | 0
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.0016866 |  | tank | 0 | 0 | 0 | 0 | 0
| Mapp Gas | tank | 12 | 812.57 | 9750.84 | 0.0002262 |  | tank | 0 | 0 | 0 | 0 | 0
| Silver Rod | pcs | 158 | 53.47 | 8448.26 | 0.00019598 |  | pcs | 0 | 0 | 0 | 0 | 0
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 | 0 | 0 | 0
IV.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 |  | lot | 0 | 0 | 0 | 0 | 0
IV.D | MISCELLANEOUS | lot | 1 | 7277.91 | 7277.91 | 0.00016883 |  | lot | 0 | 0 | 0 | 0 | 0
IV.E | TESTING & COMMISSIONING | lot | 1 | 44240.94 | 44240.94 | 0.0010263 |  | lot | 0 | 0 | 0 | 0 | 0
IV | ELECTRICAL WORKS | [7 empty] | 0 |  | 0 | 0
| Electrical Works | [7 empty] | 0 |  | 0 | 0
I. | Service Entrance | [7 empty] | 0 |  | 0 | 0
II. | Feeder | [7 empty] | 0 |  | 0 | 0
| Feeder Wire | [7 empty] | 0 |  | 0 | 0
| 250mm² THHN | m | 726 | 7092.36 | 5149053.36 | 0.11945 |  | m | 0 | 0 | 0 | 0 | 0
| 200mm² THHN | m | 117 | 5509.16 | 644571.72 | 0.014953 |  | m | 0 | 0 | 0 | 0 | 0
| 38mm² THHN | m | 390 | 1126.48 | 439327.2 | 0.010192 |  | m | 0 | 0 | 0 | 0 | 0
| for ground: | [7 empty] | 0 |  | 0 | 0
| 80mm² THHN | m | 242 | 2129.76 | 515401.92 | 0.011956 |  | m | 0 | 0 | 0 | 0 | 0
| 30mm² THHN | m | 39 | 823.69 | 32123.91 | 0.00074522 |  | m | 0 | 0 | 0 | 0 | 0
| 14mm² THHN | m | 130 | 358.87 | 46653.1 | 0.0010823 |  | m | 0 | 0 | 0 | 0 | 0
| Roughing-ins | [7 empty] | 0 |  | 0 | 0
| 90mm dia. IMC | length/s | 94 | 9301.67 | 874356.98 | 0.020284 |  | length/s | 0 | 0 | 0 | 0 | 0
| 40mm dia. IMC | length/s | 45 | 2672.9 | 120280.5 | 0.0027903 |  | length/s | 0 | 0 | 0 | 0 | 0
III. | Panel Board & Pullbox | [7 empty] | 0 |  | 0 | 0
| DP-Main | Assy | 1 | 772225.45 | 772225.45 | 0.017914 |  | Assy | 0 | 0 | 0 | 0 | 0
| Main CB: 1200AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 1 - 700AT, 3P | [7 empty] | 0 |  | 0 | 0
| 4 - 125AT, 3P | [7 empty] | 0 |  | 0 | 0
| PP-System A | Assy | 1 | 125827.11 | 125827.11 | 0.002919 |  | Assy | 0 | 0 | 0 | 0 | 0
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 2 - 40AT, 3P | [7 empty] | 0 |  | 0 | 0
| 3 - 40AT, 2P | [7 empty] | 0 |  | 0 | 0
| 9 - 30AT, 2P | [7 empty] | 0 |  | 0 | 0
| PP-System B | Assy | 1 | 135268.13 | 135268.13 | 0.003138 |  | Assy | 0 | 0 | 0 | 0 | 0
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 1 - 40AT, 3P | [7 empty] | 0 |  | 0 | 0
| 2 - 40AT, 2P | [7 empty] | 0 |  | 0 | 0
| 11 - 30AT, 2P | [7 empty] | 0 |  | 0 | 0
| PP-System C | Assy | 1 | 120190.82 | 120190.82 | 0.0027882 |  | Assy | 0 | 0 | 0 | 0 | 0
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 2 - 40AT, 3P | [7 empty] | 0 |  | 0 | 0
| 7 - 40AT, 2P | [7 empty] | 0 |  | 0 | 0
| 5 - 30AT, 2P | [7 empty] | 0 |  | 0 | 0
| PP-System D | Assy | 1 | 131472.25 | 131472.25 | 0.0030499 |  | Assy | 0 | 0 | 0 | 0 | 0
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 3 - 40AT, 3P | [7 empty] | 0 |  | 0 | 0
| 4 - 40AT, 2P | [7 empty] | 0 |  | 0 | 0
| 8 - 30AT, 2P | [7 empty] | 0 |  | 0 | 0
| PP-Outdoor | Assy | 1 | 473575.57 | 473575.57 | 0.010986 |  | Assy | 0 | 0 | 0 | 0 | 0
| Main CB: 700AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [7 empty] | 0 |  | 0 | 0
| Branches: 4 - 150AT, 3P | [7 empty] | 0 |  | 0 | 0
| Transformer | Assy | 1 | 932598.82 | 932598.82 | 0.021635 |  | Assy | 0 | 0 | 0 | 0 | 0
| 500KVA Step Down Dry Type Transformer, 480V to 230V, 3P Floor mounted, Indoor Type, 60Hz, Nema1 "TRANSPHIL" | [7 empty] | 0 |  | 0 | 0
| ECB 1250AT Nema 12 | pc | 1 | 302047.59 | 302047.59 | 0.007007 |  | pc | 0 | 0 | 0 | 0 | 0
| Pullbox (350mm x 350mm x 200mm) | pc | 5 | 5538.24 | 27691.2 | 0.00064239 |  | pc | 0 | 0 | 0 | 0 | 0
| Wire Gutter | lot | 1 | 32074.68 | 32074.68 | 0.00074408 |  | lot | 0 | 0 | 0 | 0 | 0
IV. | Mechanical System Power Supply | [7 empty] | 0 |  | 0 | 0
| ECB's | [7 empty] | 0 |  | 0 | 0
| ECB 150AT, 3P, 230V, Nema3R | pc | 4 | 29019.11 | 116076.44 | 0.0026928 |  | pc | 0 | 0 | 0 | 0 | 0
| ECB 40AT, 3P, 230V, Nema3R | pc | 7 | 11083.84 | 77586.88 | 0.0017999 |  | pc | 0 | 0 | 0 | 0 | 0
| ECB 40AT, 2P, 230V, Nema3R | pc | 16 | 9429.22 | 150867.52 | 0.0034999 |  | pc | 0 | 0 | 0 | 0 | 0
| ECB 30AT, 2P, 230V, Nema3R | pc | 23 | 9429.22 | 216872.06 | 0.0050311 |  | pc | 0 | 0 | 0 | 0 | 0
| Roughing-ins | [7 empty] | 0 |  | 0 | 0
| 40mm dia. IMC | length/s | 49 | 2672.9 | 130972.1 | 0.0030383 |  | length/s | 0 | 0 | 0 | 0 | 0
| 25mm dia. IMC | length/s | 1003 | 1753.43 | 1758690.29 | 0.040799 |  | length/s | 0 | 0 | 0 | 0 | 0
| Boxes | [7 empty] | 0 |  | 0 | 0
| Junction boxes with cover | pc/s | 195 | 125.85 | 24540.75 | 0.0005693 |  | pc/s | 0 | 0 | 0 | 0 | 0
| Wires | [7 empty] | 0 |  | 0 | 0
| 50mm² THHN | Lm/s | 429 | 1395.9 | 598841.1 | 0.013892 |  | Lm/s | 0 | 0 | 0 | 0 | 0
| 5.5mm² THHN | Lm/s | 6798 | 144.13 | 979795.74 | 0.02273 |  | Lm/s | 0 | 0 | 0 | 0 | 0
| for ground: | [7 empty] | 0 |  | 0 | 0
| 14mm² THHN | Lm/s | 143 | 358.87 | 51318.41 | 0.0011905 |  | Lm/s | 0 | 0 | 0 | 0 | 0
| 5.5mm² THHN | Lm/s | 3185 | 144.13 | 459054.05 | 0.010649 |  | Lm/s | 0 | 0 | 0 | 0 | 0
V. | Chipping & Restoration Works (Rough only) | lot | 1 | 145441.09 | 145441.09 | 0.003374 |  | lot | 0 | 0 | 0 | 0 | 0
VI. | Hangers & Supports | lot | 1 | 174529.31 | 174529.31 | 0.0040488 |  | lot | 0 | 0 | 0 | 0 | 0
VII. | Miscelleneuos | lot | 1 | 87264.66 | 87264.66 | 0.0020244 |  | lot | 0 | 0 | 0 | 0 | 0
VIII. | Testing & Commissioning | lot | 1 | 884818.61 | 884818.61 | 0.020526 |  | lot | 0 | 0 | 0 | 0 | 0
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 | 0 | 0 | 0
| Prepared by: |  | Reviewed and Submitted by: | [5 empty] | 0 | Noted by: | 0 | 0
| PROJECT ENGINEER |  | PROJECT MANAGER | [5 empty] | 0 | PROJECT DIRECTOR | 0 | 0