## Accomplishment Report
Item No. | Description of Work | Unit/s | Qty | Unit Cost | Total Cost | Weighted % | Qty | Unit/s | Total | PREVIOUS | THIS PERIOD | ACCOMPLISHMEN TO DATE | % | Remarks
I | GENERAL REQUIREMENTS
PERMITS, FEES, TAXES AND LICENSES
a. Barangay Permits
b. Local Government Permits
c. BFD Permits
d. DENR Permits
b. Contractor's All Risk Insurance (CARI)
c. Performance Bond
d. Other Insurances and Bonds
| Mobilization and Demobilization | lot | 1 | 103229 | 103229 | 0.0023947 | 1 | lot | 103229 | 103229 | 0 | 103229 | 0.0023947 | Completed
Site Management Work
| a. Project Management | lot | 1 | 678976 | 678976 | 0.015751 | 1 | lot | 678976 | 678976 | 0 | 678976 | 0.015751 | Completed
| b. Admin Support - Accounting, Procurement, Logistics | lot | 1 | 279580 | 279580 | 0.0064858 | 1 | lot | 279580 | 279580 | 0 | 279580 | 0.0064858 | Completed
| c.Quality Management | lot | 1 | 279580 | 279580 | 0.0064858 | 1 | lot | 279580 | 279580 | 0 | 279580 | 0.0064858 | Completed
| d. Engineering Management - Clarifications & Drawings | lot | 1 | 319519 | 319519 | 0.0074123 | 1 | lot | 319519 | 319519 | 0 | 319519 | 0.0074123 | Completed
Temporary Works
a. Site Office
| b. Warehouse | lot | 1 | 51615 | 51615 | 0.0011974 | 1 | lot | 51615 | 51615 | 0 | 51615 | 0.0011974 | Completed
| b. Site Office Materials & Communication | lot | 1 | 14747 | 14747 | 0.0003421 | 1 | lot | 14747 | 14747 | 0 | 14747 | 0.0003421 | Completed
| c. Temporary Tools & Cleaning Materials | lot | 1 | 7374 | 7374 | 0.00017106 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| b. Off-site Barracks - Construction and-or Rent - Electric Consumption - Water Consumption | lot | 1 | 184338 | 184338 | 0.0042763 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Temporary Utilities | [8 empty] | 0
| a. On-Site Water Consumption | [8 empty] | 0
| b. On-Site Electric Consumption | [8 empty] | 0 |  | 0 | 0
| Security, Safety and Protection | [8 empty] | 0
| a. Safety Officer | lot | 1 | 331807 | 331807 | 0.0076973 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| b. Personal Protective Equipment (PPE's) | lot | 1 | 73735 | 73735 | 0.0017105 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| b. Security Guards | lot | 1 | [6 empty] | 0 |  | 0 | 0
| Quality Standard and Control | [8 empty] | 0 |  | 0 | 0
| a. Shopdrawings, As-built plans for Occupancy including Sign & Seal | lot | 1 | 117976 | 117976 | 0.0027368 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
b. Material Testing
| Transportation | [8 empty] | 0
| a. Manpower Service | lot | 1 | 147470 | 147470 | 0.003421 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| b. Engineer Transportation | lot | 1 | 110603 | 110603 | 0.0025658 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| c. Village Delivery/Gate Pass Fees | [8 empty] | 0 |  | 0 | 0
III | MECHANICAL WORKS | [8 empty] | 0 |  | 0 | 0
| Mechanical Works | [8 empty] | 0 |  | 0 | 0
I-A. | AIR CONDITIONING- VRV SYSTEM A
| ACCU- 18HP Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 0.051574 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF A (OR No. 2, PNCOU, OR No.3, OR, Pantry, OR Complex Conference Room) Model: FXAQ50BVM | units | 6 | 55087.34 | 330524.04 | 0.0076676 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF A (OR No. 2 ENT, OR No. 1 ENT, Chief Nurse, OR Pharmacy) Model: FXAQ63BVM | units | 3 | 56222.86 | 168668.58 | 0.0039128 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF A (Corridor Near OR No.1, Corridor Near OR No. 2 ENT) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.0040611 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Accessories: | [8 empty] | 0
| Navigation Wired Controller Model: BRC1E63 | units | 11 | 11760.72 | 129367.92 | 0.0030011 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.0010367 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A22T | units | 2 | 4351.47 | 8702.94 | 0.00020189 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 2 | 4939.51 | 9879.02 | 0.00022918 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A732T | units | 3 | 8232.51 | 24697.53 | 0.00057294 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A733T | units | 3 | 14112.87 | 42338.61 | 0.00098218 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.00041743 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [8 empty] | 0
| 1/4" | length/s | 10 | 2120.33 | 21203.3 | 0.00049188 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 13 | 2952.35 | 38380.55 | 0.00089036 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 14 | 4696.92 | 65756.88 | 0.0015254 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 9 | 6775.95 | 60983.55 | 0.0014147 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 9 | 8642.33 | 77780.97 | 0.0018044 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 10870.01 | 21740.02 | 0.00050433 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 8 | 15566.92 | 124535.36 | 0.002889 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 5 | 21015.33 | 105076.65 | 0.0024376 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 4 | 21015.33 | 84061.32 | 0.0019501 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
Copper Pipes Insulation 25mm Thick
| 1/4" | length/s | 19 | 433.57 | 8237.83 | 0.0001911 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 26 | 441.83 | 11487.58 | 0.00026649 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 27 | 516.15 | 13936.05 | 0.00032329 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 18 | 629.71 | 11334.78 | 0.00026295 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 17 | 708.16 | 12038.72 | 0.00027928 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 4 | 784.55 | 3138.2 | 7.2801e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 15 | 846.49 | 12697.35 | 0.00029456 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 10 | 896.03 | 8960.3 | 0.00020786 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 8 | 896.03 | 7168.24 | 0.00016629 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 57975.92 | 57975.92 | 0.0013449 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 22 | 3207.48 | 70564.56 | 0.001637 |  | pc/s | 0 | 0 |  | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 22281.85 | 22281.85 | 0.0005169 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs |  | 0 |  | 0 | 0 | Ongoing
| Condensate Drain Pipes | [8 empty] | 0 |  | 0 | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 39 | 404.15 | 15761.85 | 0.00036565 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 22 | 641.83 | 14120.26 | 0.00032757 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
Condensate Drain Pipes Rubber Insulation 1.5 meters
| 3/4'' thick for 32mm pvc | length/s | 77 | 427.67 | 32930.59 | 0.00076393 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 43 | 812.57 | 34940.51 | 0.00081056 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Drain Pump | [8 empty] | 0 |  | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 9 | 30473.16 | 274258.44 | 0.0063623 |  | pcs |  | 0 |  | 0 | 0 | Ongoing
[9 empty] | 0 | 0 |  | 0 | 0
| Fittings | [8 empty] | 0 |  | 0 | 0
| Wye Reducer 50 x 32 | pcs | 11 | 192.46 | 2117.06 | 4.9112e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Tee 32mm | pcs | 2 | 53.47 | 106.94 | 2.4808e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Tee Reducer 50 x 32 | pcs | 2 | 203.15 | 406.3 | 9.4255e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Elbow 32mm | pcs | 6 | 43.63 | 261.78 | 6.0728e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Cleanout 50mm | pcs | 4 | 213.84 | 855.36 | 1.9843e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [8 empty] | 0
| Rough-ins | [8 empty] | 0
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.0007313 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit 20mm | m | 586 | 65.87 | 38599.82 | 0.00089545 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 29 | 32.09 | 930.61 | 2.1589e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Cables / Wires | [8 empty] | 0 |  | 0 | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 419 | 80.84 | 33871.96 | 0.00078577 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 71 | 78.48 | 5572.08 | 0.00012926 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 7.2445e-05 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 790.33 | 46629.47 | 0.0010817 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0 |  | 0 | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 72 | 78.48 | 5650.56 | 0.00013108 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 8.717e-05 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
I-B. | CONSUMABLES | [8 empty] | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Rugby | bottle | 21 | 277.99 | 5837.79 | 0.00013543 |  | bottle | 0 | 0 |  | 0 | 0 | Ongoing
| White Tape | rolls | 42 | 374.22 | 15717.24 | 0.00036461 |  | rolls | 0 | 0 |  | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 94 | 171.07 | 16080.58 | 0.00037304 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 |  | 0 | 0 | Ongoing
| Loop Hangers | pcs | 351 | 42.78 | 15015.78 | 0.00034834 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Freon | tank | 6 | 14497.77 | 86986.62 | 0.0020179 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Nitrogen | tank | 3 | 18175.66 | 54526.98 | 0.0012649 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Mapp Gas | tank | 11 | 855.33 | 9408.63 | 0.00021826 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Silver Rod | pcs | 141 | 53.47 | 7539.27 | 0.0001749 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
I-C. | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
I-D. | MISCELLANEOUS | lot | 1 | 5684.06 | 5684.06 | 0.00013186 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
I-E. | TESTING & COMMISSIONING | lot | 1 | 41291.54 | 41291.54 | 0.00095789 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
II.A | AIR CONDITIONING- VRV SYSTEM B | [8 empty] | 0
| ACCU- Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 0.051574 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF B (OR No. 1 and 3, OR No. 1 Miyake Eye (2), OR No. 2 NSS(2), OR No. 3 Euro-open (2), OR No. 8 Ortho, NSS/ Pay, Storage Room, OR Complex Conference Room) Model: FXAQ50BVM | units | 10 | 55087.34 | 550873.4 | 0.012779 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF B ( OR no. 4, 6, 13, 14, 15, OR Pharmacy) Model: FXAQ63BVM | units | 2 | 56222.86 | 112445.72 | 0.0026085 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF B (Corridor near OR No. 2 NSS, Corridor Near Supply Room) Model: FXFQ140AVM | units | 1 | 87530.69 | 87530.69 | 0.0020306 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Accessories: | [8 empty] | 0 |  | 0 | 0
| Wired Remote Controller Model: BRC1E63 | units | 13 | 11760.72 | 152889.36 | 0.0035468 |  | units |  | 0 |  | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 1 | 22345.37 | 22345.37 | 0.00051837 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A22T | units | 6 | 4351.47 | 26108.82 | 0.00060568 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 1 | 4939.51 | 4939.51 | 0.00011459 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A72T | units | 3 | 8232.51 | 24697.53 | 0.00057294 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A73T | units | 2 | 14112.87 | 28225.74 | 0.00065479 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 2 | 5997.97 | 11995.94 | 0.00027828 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [8 empty] | 0 |  | 0 | 0
| 1/4" | length/s | 14 | 2120.33 | 29684.62 | 0.00068863 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 11 | 2952.35 | 32475.85 | 0.00075338 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 15 | 4696.92 | 70453.8 | 0.0016344 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 12 | 6775.95 | 81311.4 | 0.0018863 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 13 | 8642.33 | 112350.29 | 0.0026063 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 1 | 10870.01 | 10870.01 | 0.00025217 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.0018056 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 1 | 27039.77 | 27039.77 | 0.00062728 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 12 | 27039.77 | 324477.24 | 0.0075273 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipes Insulation 25mm Thick | [8 empty] | 0 |  | 0 | 0
| 1/4" | length/s | 27 | 433.57 | 11706.39 | 0.00027157 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 21 | 441.83 | 9278.43 | 0.00021524 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 30 | 516.15 | 15484.5 | 0.00035921 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 24 | 629.71 | 15113.04 | 0.0003506 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 26 | 708.16 | 18412.16 | 0.00042713 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 784.55 | 1569.1 | 3.64e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 9 | 846.49 | 7618.41 | 0.00017673 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 2 | 1011.66 | 2023.32 | 4.6938e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 24 | 1011.66 | 24279.84 | 0.00056325 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 87733.46 | 87733.46 | 0.0020353 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 26 | 3207.48 | 83394.48 | 0.0019346 |  | pc/s | 0 | 0 |  | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 8234.77 | 8234.77 | 0.00019103 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Condensate Drain Pipes | [8 empty] | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 37 | 404.15 | 14953.55 | 0.0003469 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 24 | 641.83 | 15403.92 | 0.00035734 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Condensate Drain Pipes Rubber Insulation 1.5 meters | [8 empty] | 0 |  | 0 | 0
| 3/4'' thick for 32mm pvc | length/s | 74 | 427.67 | 31647.58 | 0.00073417 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 48 | 812.57 | 39003.36 | 0.00090481 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Drain Pump | [8 empty] | 0 |  | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 12 | 30473.16 | 365677.92 | 0.0084831 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Fittings | [8 empty] | 0 |  | 0 | 0
| Wye 50mm | pcs | 3 | 213.84 | 641.52 | 1.4882e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Wye Reducer 50 x 32 | pcs | 13 | 192.46 | 2501.98 | 5.8042e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Tee 32mm | pcs | 3 | 53.47 | 160.41 | 3.7212e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Elbow 32mm | pcs | 6 | 43.63 | 261.78 | 6.0728e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Cleanout 50mm | pcs | 4 | 213.84 | 855.36 | 1.9843e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [8 empty] | 0 |  | 0 | 0
| Rough-ins | [8 empty] | 0 |  | 0 | 0
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.0007313 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit | m | 673 | 65.87 | 44330.51 | 0.0010284 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 34 | 32.09 | 1091.06 | 2.5311e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Cables / Wires | [8 empty] | 0 |  | 0 | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 482 | 80.84 | 38964.88 | 0.00090392 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 94 | 78.48 | 7377.12 | 0.00017114 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 13 | 115.83 | 1505.79 | 3.4932e-05 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 789.47 | 46578.73 | 0.0010805 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0 |  | 0 | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 85 | 78.48 | 6670.8 | 0.00015475 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 8.717e-05 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
II.B | CONSUMABLES | [8 empty] | 0 |  | 0 | 0
| Vibration Isolator | pcs | 16 | 1389.91 | 22238.56 | 0.0005159 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 6 | 2523.22 | 15139.32 | 0.00035121 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Rugby | bottle | 25 | 277.99 | 6949.75 | 0.00016122 |  | bottle | 0 | 0 |  | 0 | 0 | Ongoing
| White Tape | rolls | 49 | 374.22 | 18336.78 | 0.00042538 |  | rolls | 0 | 0 |  | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 107 | 171.07 | 18304.49 | 0.00042463 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 |  | 0 | 0 | Ongoing
| Loop Hangers | pcs | 402 | 42.78 | 17197.56 | 0.00039895 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Freon | tank | 7 | 14497.77 | 101484.39 | 0.0023543 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.0016866 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Mapp Gas | tank | 12 | 855.33 | 10263.96 | 0.00023811 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Silver Rod | pcs | 160 | 53.47 | 8555.2 | 0.00019847 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
II.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
II.D | MISCELLANEOUS | lot | 1 | 6640.71 | 6640.71 | 0.00015405 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
II.E | TESTING & COMMISIONING | lot | 1 | 47190.33 | 47190.33 | 0.0010947 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
III.A | AIR CONDITIONING- VRV SYSTEM C | [8 empty] | 0 |  | 0 | 0
| ACCU- Model: RXQ18BYM | units | 3 | 741057.71 | 2223173.13 | 0.051574 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF C (Storage Room, OR No. 8 Ortho, NSS/Pay, OR No. 9 Plastic Surgery (2) ) Model: FXAQ50BVM | units | 1 | 55087.34 | 55087.34 | 0.0012779 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF C (OR No. 4, Euro- Endo (2), OR No. 7 Ortho, OR. 12 Pedia, OR No. 10 Pay) Model: FXAQ63BVM | units | 7 | 56222.86 | 393560.02 | 0.0091299 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF C (Corridor near Ortho, Corridor near OR. No. 10, Corridor near NSS/Pay) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.0040611 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Accessories: | [8 empty] | 0
| Wired Remote Controller Model: BRC1E63 | units | 10 | 11760.72 | 117607.2 | 0.0027283 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.0010367 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 2 | 4939.51 | 9879.02 | 0.00022918 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A72T | units | 4 | 8232.51 | 32930.04 | 0.00076392 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A73T | units | 3 | 14112.87 | 42338.61 | 0.00098218 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.00041743 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [8 empty] | 0
| 1/4" | length/s | 1 | 2120.33 | 2120.33 | 4.9188e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 11 | 2952.35 | 32475.85 | 0.00075338 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 2 | 4696.92 | 9393.84 | 0.00021792 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 14 | 6775.95 | 94863.3 | 0.0022007 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 9 | 8642.33 | 77780.97 | 0.0018044 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 1 | 10870.01 | 10870.01 | 0.00025217 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.0018056 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 3 | 21015.33 | 63045.99 | 0.0014626 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 7 | 27039.77 | 189278.39 | 0.0043909 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
Copper Pipes Insulation 25mm Thick
| 1/4" | length/s | 2 | 433.57 | 867.14 | 2.0116e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 21 | 441.83 | 9278.43 | 0.00021524 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 4 | 516.15 | 2064.6 | 4.7895e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 27 | 629.71 | 17002.17 | 0.00039442 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 17 | 708.16 | 12038.72 | 0.00027928 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 784.55 | 1569.1 | 3.64e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 10 | 846.49 | 8464.9 | 0.00019637 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 5 | 896.03 | 4480.15 | 0.00010393 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 13 | 1011.66 | 13151.58 | 0.00030509 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 59135.15 | 59135.15 | 0.0013718 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 20 | 3207.48 | 64149.6 | 0.0014882 |  | pc/s | 0 | 0 |  | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 19711.72 | 19711.72 | 0.00045728 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Condensate Drain Pipes | [8 empty] | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 33 | 404.15 | 13336.95 | 0.00030939 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 12 | 641.83 | 7701.96 | 0.00017867 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Condensate Drain Pipes Rubber Insulation 1.5 meters | [8 empty] | 0 |  | 0 | 0
| 3/4'' thick for 32mm pvc | length/s | 66 | 427.67 | 28226.22 | 0.0006548 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 23 | 812.57 | 18689.11 | 0.00043355 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Drain Pump | [8 empty] | 0 |  | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 11 | 30473.16 | 335204.76 | 0.0077762 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Fittings | [8 empty] | 0 |  | 0 | 0
| Wye Reducer 50 x 32 | length/s | 7 | 192.46 | 1347.22 | 3.1253e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Tee 32mm | length/s | 6 | 53.47 | 320.82 | 7.4425e-06 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Elbow 32mm | length/s | 7 | 43.63 | 305.41 | 7.085e-06 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Cleanout 50mm | length/s | 2 | 213.84 | 427.68 | 9.9214e-06 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [8 empty] | 0 |  | 0 | 0
| Rough-ins | [8 empty] | 0 |  | 0 | 0
| liquid-tight metallic flexible conduits 1-1/2" | m | 78 | 404.15 | 31523.7 | 0.0007313 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit 20mm | m | 444 | 65.87 | 29246.28 | 0.00067846 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 26 | 32.09 | 834.34 | 1.9355e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Cables / Wires | [8 empty] | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 291 | 80.84 | 23524.44 | 0.00054573 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 63 | 78.49 | 4944.87 | 0.00011471 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 7.2445e-05 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 30.0mm² THHN (5 meters per Unit) | m | 59 | 789.47 | 46578.73 | 0.0010805 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 65 | 78.49 | 5101.85 | 0.00011835 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 8.0mm² THHN (G) (5 meters per Unit) | m | 20 | 187.88 | 3757.6 | 8.717e-05 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
III.B | CONSUMABLES | [8 empty] | 0 |  | 0 | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Rugby | bottle | 15 | 277.99 | 4169.85 | 9.6733e-05 |  | bottle | 0 | 0 |  | 0 | 0 | Ongoing
| White Tape | rolls | 30 | 374.22 | 11226.6 | 0.00026044 |  | rolls | 0 | 0 |  | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 65 | 171.07 | 11119.55 | 0.00025795 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 |  | 0 | 0 | Ongoing
| Loop Hangers | pcs | 244 | 42.78 | 10438.32 | 0.00024215 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Freon | tank | 5 | 14497.77 | 72488.85 | 0.0016816 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Nitrogen | tank | 3 | 18175.66 | 54526.98 | 0.0012649 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Mapp Gas | tank | 8 | 812.57 | 6500.56 | 0.0001508 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Silver Rod | pcs | 98 | 53.47 | 5240.06 | 0.00012156 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
III.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
III.D | MISCELLANEOUS | lot | 1 | 5010.49 | 5010.49 | 0.00011623 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
III.E | TESTING & COMMISSIONING | lot | 1 | 38342.14 | 38342.14 | 0.00088947 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV.A | AIR CONDITIONING- VRV SYSTEM D | [8 empty] | 0 |  | 0 | 0
| ACCU- Model: RXQ20BYM | units | 3 | 789317.19 | 2367951.57 | 0.054932 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2 HP Wall Mounted VRF C (Storage Room, OR No. 8 Ortho, NSS/Pay, OR No. 9 Plastic Surgery (2) ) Model: FXAQ50BVM | units | 6 | 55087.34 | 330524.04 | 0.0076676 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 2.5HP Wall Mounted VRF C (OR No. 4, Euro- Endo (2), OR No. 7 Ortho, OR. 12 Pedia, OR No. 10 Pay) Model: FXAQ63BVM | units | 4 | 56222.86 | 224891.44 | 0.0052171 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| FCU- 6HP ceiling Cassette VRF C (Corridor near Ortho, Corridor near OR. No. 10, Corridor near NSS/Pay) Model: FXFQ140AVM | units | 2 | 87530.69 | 175061.38 | 0.0040611 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Accessories: | [8 empty] | 0
| Wired Remote Controller Model: BRC1E63 | units | 12 | 11760.72 | 141128.64 | 0.0032739 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Standard panel(Fresh white) Model: BYCQ125EAF | units | 2 | 22345.37 | 44690.74 | 0.0010367 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A22T | units | 4 | 4351.47 | 17405.88 | 0.00040379 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A33T | units | 1 | 4939.51 | 4939.51 | 0.00011459 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A72T | units | 3 | 8232.51 | 24697.53 | 0.00057294 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Refnet Joints Model: KHRP26A73T | units | 3 | 14112.87 | 42338.61 | 0.00098218 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Pipe Size Reducer Model: KHRP26M73TP | units | 3 | 5997.97 | 17993.91 | 0.00041743 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| VRV Multi Con piping kit Model: BHFP22R168-7 | units | 1 | 39751.22 | 39751.22 | 0.00092216 |  | units | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipes - Type L Hard Drawn Pipes | [8 empty] | 0 |  | 0 | 0
| 1/4" | length/s | 8 | 2120.33 | 16962.64 | 0.0003935 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 12 | 2952.35 | 35428.2 | 0.00082187 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 10 | 4696.92 | 46969.2 | 0.0010896 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 14 | 6775.95 | 94863.3 | 0.0022007 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 16 | 8642.33 | 138277.28 | 0.0032078 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 2 | 10870.01 | 21740.02 | 0.00050433 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 5 | 15566.92 | 77834.6 | 0.0018056 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 2 | 21015.33 | 42030.66 | 0.00097504 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 14 | 27039.77 | 378556.78 | 0.0087819 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipes Insulation 25mm Thick | [8 empty] | 0
| 1/4" | length/s | 16 | 433.57 | 6937.12 | 0.00016093 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/8" | length/s | 24 | 441.83 | 10603.92 | 0.00024599 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1/2" | length/s | 19 | 516.15 | 9806.85 | 0.0002275 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5/8" | length/s | 27 | 629.71 | 17002.17 | 0.00039442 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4" | length/s | 31 | 708.16 | 21952.96 | 0.00050927 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 7/8" | length/s | 4 | 784.55 | 3138.2 | 7.2801e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-1/8" | length/s | 10 | 846.49 | 8464.9 | 0.00019637 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-3/8" | length/s | 4 | 896.03 | 3584.12 | 8.3145e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 1-5/8" | length/s | 27 | 1011.66 | 27314.82 | 0.00063366 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Copper Pipe Fittings | lot | 1 | 96659.97 | 96659.97 | 0.0022423 |  | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Isolation Ball Valves | pc/s | 24 | 3207.48 | 76979.52 | 0.0017858 |  | pc/s | 0 | 0 |  | 0 | 0 | Ongoing
| PVC Cladding Works | lot | 1 | 32220 | 32220 | 0.00074745 |  | lot | 0 | 0 |  | 0 | 0 | Ongoing
| Concrete Pad | pcs | 3 | 9622.41 | 28867.23 | 0.00066967 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Condensate Drain Pipes | [8 empty] | 0 |  | 0 | 0
| 32mm dia. uPVC blue pipe PNS 65 | length/s | 31 | 404.15 | 12528.65 | 0.00029064 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 50mm dia. PVC blue uPVC blue pipe PNS 65 | length/s | 38 | 641.83 | 24389.54 | 0.00056579 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Condensate Drain Pipes Rubber Insulation 1.5 meters | [8 empty] | 0
| 3/4'' thick for 32mm pvc | length/s | 61 | 427.67 | 26087.87 | 0.00060519 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 3/4'' thick for 50mm pvc | length/s | 75 | 812.57 | 60942.75 | 0.0014138 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Drain Pump | [8 empty] | 0 |  | 0 | 0
| (5.0m pump Lift) Model: BDU513A450VE | pcs | 10 | 30473.16 | 304731.6 | 0.0070692 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Fittings | [8 empty] | 0
| Wye 50mm | length/s | 2 | 213.84 | 427.68 | 9.9214e-06 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Wye Reducer 50 x 32 | length/s | 11 | 192.46 | 2117.06 | 4.9112e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Tee 32mm | length/s | 3 | 53.47 | 160.41 | 3.7212e-06 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Tee Reducer 50 x 32 | length/s | 3 | 203.15 | 609.45 | 1.4138e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Elbow 32mm | length/s | 7 | 43.63 | 305.41 | 7.085e-06 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Cleanout 50mm | length/s | 6 | 213.84 | 1283.04 | 2.9764e-05 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| RELATED ELECTRICAL WORKS | [8 empty] | 0 |  | 0 | 0
| Rough-ins | [8 empty] | 0
| liquid-tight metallic flexible conduits 2" | m | 78 | 763.39 | 59544.42 | 0.0013813 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit 20mm | m | 654 | 65.87 | 43078.98 | 0.00099936 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Metallic Flexible Conduit Connector 20mm | pcs | 32 | 32.09 | 1026.88 | 2.3822e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Cables / Wires | [8 empty] | 0 |  | 0 | 0
| Communication wire (PD Royal Cord 0.75mm/2C) | m | 472 | 80.84 | 38156.48 | 0.00088516 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 3.5mm² THHN (5 meters per Unit) | m | 78 | 77.05 | 6009.9 | 0.00013942 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 5.5mm² THHN (5 meters per Unit) | m | 26 | 120.11 | 3122.86 | 7.2445e-05 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 38.0mm² THHN (5 meters per Unit) | m | 59 | 938.2 | 55353.8 | 0.0012841 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0 |  | 0 | 0
| Wire 3.5mm² THHN (G) (5 meters per Unit) | m | 78 | 75.36 | 5878.08 | 0.00013636 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Wire 14.0mm² THHN (G) (5 meters per Unit) | m | 20 | 311.01 | 6220.2 | 0.0001443 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
IV.B | CONSUMABLES | [8 empty] | 0 |  | 0 | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Rugby | bottle | 24 | 277.99 | 6671.76 | 0.00015477 |  | bottle | 0 | 0 |  | 0 | 0 | Ongoing
| White Tape | rolls | 47 | 374.22 | 17588.34 | 0.00040802 |  | rolls | 0 | 0 |  | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 104 | 171.07 | 17791.28 | 0.00041273 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 |  | 0 | 0 | Ongoing
| Loop Hangers | pcs | 393 | 42.78 | 16812.54 | 0.00039002 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Freon | tank | 8 | 14497.77 | 115982.16 | 0.0026906 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.0016866 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Mapp Gas | tank | 12 | 812.57 | 9750.84 | 0.0002262 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Silver Rod | pcs | 158 | 53.47 | 8448.26 | 0.00019598 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
IV.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV.D | MISCELLANEOUS | lot | 1 | 7277.91 | 7277.91 | 0.00016883 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV.E | TESTING & COMMISSIONING | lot | 1 | 44240.94 | 44240.94 | 0.0010263 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV | ELECTRICAL WORKS | [8 empty] | 0 |  | 0 | 0
| Electrical Works | [8 empty] | 0 |  | 0 | 0
I. | Service Entrance | [8 empty] | 0 |  | 0 | 0
II. | Feeder | [8 empty] | 0 |  | 0 | 0
| Feeder Wire | [8 empty] | 0 |  | 0 | 0
| 250mm² THHN | m | 726 | 7092.36 | 5149053.36 | 0.11945 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 200mm² THHN | m | 117 | 5509.16 | 644571.72 | 0.014953 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 38mm² THHN | m | 390 | 1126.48 | 439327.2 | 0.010192 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0
| 80mm² THHN | m | 242 | 2129.76 | 515401.92 | 0.011956 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 30mm² THHN | m | 39 | 823.69 | 32123.91 | 0.00074522 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 14mm² THHN | m | 130 | 358.87 | 46653.1 | 0.0010823 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| Roughing-ins | [8 empty] | 0 |  | 0 | 0
| 90mm dia. IMC | length/s | 94 | 9301.67 | 874356.98 | 0.020284 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 40mm dia. IMC | length/s | 45 | 2672.9 | 120280.5 | 0.0027903 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
III. | Panel Board & Pullbox | [8 empty] | 0 |  | 0 | 0
| DP-Main | Assy | 1 | 772225.45 | 772225.45 | 0.017914 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 1200AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0 |  | 0 | 0
| Branches: 1 - 700AT, 3P | [8 empty] | 0 |  | 0 | 0
| 4 - 125AT, 3P | [8 empty] | 0
| PP-System A | Assy | 1 | 125827.11 | 125827.11 | 0.002919 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0 |  | 0 | 0
| Branches: 2 - 40AT, 3P | [8 empty] | 0 |  | 0 | 0
| 3 - 40AT, 2P | [8 empty] | 0 |  | 0 | 0
| 9 - 30AT, 2P | [8 empty] | 0 |  | 0 | 0
| PP-System B | Assy | 1 | 135268.13 | 135268.13 | 0.003138 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0 |  | 0 | 0
| Branches: 1 - 40AT, 3P | [8 empty] | 0 |  | 0 | 0
| 2 - 40AT, 2P | [8 empty] | 0 |  | 0 | 0
| 11 - 30AT, 2P | [8 empty] | 0 |  | 0 | 0
| PP-System C | Assy | 1 | 120190.82 | 120190.82 | 0.0027882 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0 |  | 0 | 0
| Branches: 2 - 40AT, 3P | [8 empty] | 0
| 7 - 40AT, 2P | [8 empty] | 0 |  | 0 | 0
| 5 - 30AT, 2P | [8 empty] | 0
| PP-System D | Assy | 1 | 131472.25 | 131472.25 | 0.0030499 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0
| Branches: 3 - 40AT, 3P | [8 empty] | 0 |  | 0 | 0
| 4 - 40AT, 2P | [8 empty] | 0
| 8 - 30AT, 2P | [8 empty] | 0
| PP-Outdoor | Assy | 1 | 473575.57 | 473575.57 | 0.010986 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 700AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0 |  | 0 | 0
| Branches: 4 - 150AT, 3P | [8 empty] | 0
| Transformer | Assy | 1 | 932598.82 | 932598.82 | 0.021635 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| 500KVA Step Down Dry Type Transformer, 480V to 230V, 3P Floor mounted, Indoor Type, 60Hz, Nema1 "TRANSPHIL" | [8 empty] | 0 |  | 0 | 0
| ECB 1250AT Nema 12 | pc | 1 | 302047.59 | 302047.59 | 0.007007 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| Pullbox (350mm x 350mm x 200mm) | pc | 5 | 5538.24 | 27691.2 | 0.00064239 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| Wire Gutter | lot | 1 | 32074.68 | 32074.68 | 0.00074408 |  | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV. | Mechanical System Power Supply | [8 empty] | 0 |  | 0 | 0
| ECB's | [8 empty] | 0
| ECB 150AT, 3P, 230V, Nema3R | pc | 4 | 29019.11 | 116076.44 | 0.0026928 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 40AT, 3P, 230V, Nema3R | pc | 7 | 11083.84 | 77586.88 | 0.0017999 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 40AT, 2P, 230V, Nema3R | pc | 16 | 9429.22 | 150867.52 | 0.0034999 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 30AT, 2P, 230V, Nema3R | pc | 23 | 9429.22 | 216872.06 | 0.0050311 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| Roughing-ins | [8 empty] | 0 |  | 0 | 0
| 40mm dia. IMC | length/s | 49 | 2672.9 | 130972.1 | 0.0030383 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 25mm dia. IMC | length/s | 1003 | 1753.43 | 1758690.29 | 0.040799 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
Boxes
| Junction boxes with cover | pc/s | 195 | 125.85 | 24540.75 | 0.0005693 |  | pc/s | 0 | 0 |  | 0 | 0 | Ongoing
| Wires | [8 empty] | 0
| 50mm² THHN | Lm/s | 429 | 1395.9 | 598841.1 | 0.013892 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 6798 | 144.13 | 979795.74 | 0.02273 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0 |  | 0 | 0
| 14mm² THHN | Lm/s | 143 | 358.87 | 51318.41 | 0.0011905 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 3185 | 144.13 | 459054.05 | 0.010649 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
V. | Chipping & Restoration Works (Rough only) | lot | 1 | 145441.09 | 145441.09 | 0.003374 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VI. | Hangers & Supports | lot | 1 | 174529.31 | 174529.31 | 0.0040488 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VII. | Miscelleneuos | lot | 1 | 87264.66 | 87264.66 | 0.0020244 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VIII. | Testing & Commissioning | lot | 1 | 884818.61 | 884818.61 | 0.020526 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 |  | 0 | 0 | Ongoing
IV.B | CONSUMABLES | [8 empty] | 0 |  | 0 | 0
| Vibration Isolator | pcs | 20 | 1389.91 | 27798.2 | 0.00064487 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Angle Bar, 2x2x 1/4 (6 meters) | length/s | 7 | 2523.22 | 17662.54 | 0.00040974 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Rugby | bottle | 24 | 277.99 | 6671.76 | 0.00015477 |  | bottle | 0 | 0 |  | 0 | 0 | Ongoing
| White Tape | rolls | 47 | 374.22 | 17588.34 | 0.00040802 |  | rolls | 0 | 0 |  | 0 | 0 | Ongoing
| Threaded rod 3/8 (6 meters) | length/s | 104 | 171.07 | 17791.28 | 0.00041273 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Nuts and washer 3/8 | pcs | 32 | 21.39 | 684.48 | 1.5879e-05 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Grip Anchor 3/8 | pcs | 32 | 10.7 | 342.4 | 7.9431e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint (Red Oxide) | gallon | 1 | 3432 | 3432 | 7.9616e-05 |  | gallon | 0 | 0 |  | 0 | 0 | Ongoing
| Loop Hangers | pcs | 393 | 42.78 | 16812.54 | 0.00039002 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Freon | tank | 8 | 14497.77 | 115982.16 | 0.0026906 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Nitrogen | tank | 4 | 18175.66 | 72702.64 | 0.0016866 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Mapp Gas | tank | 12 | 812.57 | 9750.84 | 0.0002262 |  | tank | 0 | 0 |  | 0 | 0 | Ongoing
| Silver Rod | pcs | 158 | 53.47 | 8448.26 | 0.00019598 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
| Paint Brush | pcs | 1 | 213.84 | 213.84 | 4.9607e-06 |  | pcs | 0 | 0 |  | 0 | 0 | Ongoing
IV.C | CHIPPING & RESTORATION (ROUGH-ONLY) | lot | 1 | 737348.84 | 737348.84 | 0.017105 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV.D | MISCELLANEOUS | lot | 1 | 7277.91 | 7277.91 | 0.00016883 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV.E | TESTING & COMMISSIONING | lot | 1 | 44240.94 | 44240.94 | 0.0010263 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV | ELECTRICAL WORKS | [8 empty] | 0 |  | 0 | 0
| Electrical Works | [8 empty] | 0
I. | Service Entrance | [8 empty] | 0 |  | 0 | 0
II. | Feeder | [8 empty] | 0
| Feeder Wire | [8 empty] | 0 |  | 0 | 0
| 250mm² THHN | m | 726 | 7092.36 | 5149053.36 | 0.11945 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 200mm² THHN | m | 117 | 5509.16 | 644571.72 | 0.014953 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 38mm² THHN | m | 390 | 1126.48 | 439327.2 | 0.010192 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
for ground:
| 80mm² THHN | m | 242 | 2129.76 | 515401.92 | 0.011956 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 30mm² THHN | m | 39 | 823.69 | 32123.91 | 0.00074522 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
| 14mm² THHN | m | 130 | 358.87 | 46653.1 | 0.0010823 |  | m | 0 | 0 |  | 0 | 0 | Ongoing
Roughing-ins
| 90mm dia. IMC | length/s | 94 | 9301.67 | 874356.98 | 0.020284 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 40mm dia. IMC | length/s | 45 | 2672.9 | 120280.5 | 0.0027903 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
III. | Panel Board & Pullbox | [8 empty] | 0 |  | 0 | 0
| DP-Main | Assy | 1 | 772225.45 | 772225.45 | 0.017914 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 1200AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0
| Branches: 1 - 700AT, 3P | [8 empty] | 0 |  | 0 | 0
| 4 - 125AT, 3P | [8 empty] | 0 |  | 0 | 0
| PP-System A | Assy | 1 | 125827.11 | 125827.11 | 0.002919 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0
| Branches: 2 - 40AT, 3P | [8 empty] | 0 |  | 0 | 0
| 3 - 40AT, 2P | [8 empty] | 0 |  | 0 | 0
9 - 30AT, 2P
| PP-System B | Assy | 1 | 135268.13 | 135268.13 | 0.003138 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0 |  | 0 | 0
Branches: 1 - 40AT, 3P
2 - 40AT, 2P
11 - 30AT, 2P
| PP-System C | Assy | 1 | 120190.82 | 120190.82 | 0.0027882 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0 |  | 0 | 0
Branches: 2 - 40AT, 3P
7 - 40AT, 2P
5 - 30AT, 2P
| PP-System D | Assy | 1 | 131472.25 | 131472.25 | 0.0030499 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
| Main CB: 125AT, 3P, 230V, 60Hz, Bolt-on Nema12 | [8 empty] | 0
| Branches: 3 - 40AT, 3P | [8 empty] | 0 |  | 0 | 0
4 - 40AT, 2P
8 - 30AT, 2P
| PP-Outdoor | Assy | 1 | 473575.57 | 473575.57 | 0.010986 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
Main CB: 700AT, 3P, 230V, 60Hz, Bolt-on Nema12
| Branches: 4 - 150AT, 3P | [8 empty] | 0
| Transformer | Assy | 1 | 932598.82 | 932598.82 | 0.021635 |  | Assy | 0 | 0 |  | 0 | 0 | Ongoing
500KVA Step Down Dry Type Transformer, 480V to 230V, 3P Floor mounted, Indoor Type, 60Hz, Nema1 "TRANSPHIL"
| ECB 1250AT Nema 12 | pc | 1 | 302047.59 | 302047.59 | 0.007007 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| Pullbox (350mm x 350mm x 200mm) | pc | 5 | 5538.24 | 27691.2 | 0.00064239 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| Wire Gutter | lot | 1 | 32074.68 | 32074.68 | 0.00074408 |  | lot | 0 | 0 |  | 0 | 0 | Ongoing
IV. | Mechanical System Power Supply | [8 empty] | 0
| ECB's | [8 empty] | 0 |  | 0 | 0
| ECB 150AT, 3P, 230V, Nema3R | pc | 4 | 29019.11 | 116076.44 | 0.0026928 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 40AT, 3P, 230V, Nema3R | pc | 7 | 11083.84 | 77586.88 | 0.0017999 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 40AT, 2P, 230V, Nema3R | pc | 16 | 9429.22 | 150867.52 | 0.0034999 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 30AT, 2P, 230V, Nema3R | pc | 23 | 9429.22 | 216872.06 | 0.0050311 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| Roughing-ins | [8 empty] | 0
| 40mm dia. IMC | length/s | 49 | 2672.9 | 130972.1 | 0.0030383 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 25mm dia. IMC | length/s | 1003 | 1753.43 | 1758690.29 | 0.040799 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
Boxes
| Junction boxes with cover | pc/s | 195 | 125.85 | 24540.75 | 0.0005693 |  | pc/s | 0 | 0 |  | 0 | 0 | Ongoing
| Wires | [8 empty] | 0 |  | 0 | 0
| 50mm² THHN | Lm/s | 429 | 1395.9 | 598841.1 | 0.013892 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 6798 | 144.13 | 979795.74 | 0.02273 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0 |  | 0 | 0
| 14mm² THHN | Lm/s | 143 | 358.87 | 51318.41 | 0.0011905 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 3185 | 144.13 | 459054.05 | 0.010649 | 100 | Lm/s | 14413 | 0 | 14413 | 0 | 0 | Ongoing
V. | Chipping & Restoration Works (Rough only) | lot | 1 | 145441.09 | 145441.09 | 0.003374 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VI. | Hangers & Supports | lot | 1 | 174529.31 | 174529.31 | 0.0040488 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VII. | Miscelleneuos | lot | 1 | 87264.66 | 87264.66 | 0.0020244 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VIII. | Testing & Commissioning | lot | 1 | 884818.61 | 884818.61 | 0.020526 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 40AT, 2P, 230V, Nema3R | pc | 16 | 9429.22 | 150867.52 | 0.0034999 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| ECB 30AT, 2P, 230V, Nema3R | pc | 23 | 9429.22 | 216872.06 | 0.0050311 |  | pc | 0 | 0 |  | 0 | 0 | Ongoing
| Roughing-ins | [8 empty] | 0 |  | 0 | 0
| 40mm dia. IMC | length/s | 49 | 2672.9 | 130972.1 | 0.0030383 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| 25mm dia. IMC | length/s | 1003 | 1753.43 | 1758690.29 | 0.040799 |  | length/s | 0 | 0 |  | 0 | 0 | Ongoing
| Boxes | [8 empty] | 0 |  | 0 | 0
| Junction boxes with cover | pc/s | 195 | 125.85 | 24540.75 | 0.0005693 |  | pc/s | 0 | 0 |  | 0 | 0 | Ongoing
| Wires | [8 empty] | 0 |  | 0 | 0
| 50mm² THHN | Lm/s | 429 | 1395.9 | 598841.1 | 0.013892 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 6798 | 144.13 | 979795.74 | 0.02273 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| for ground: | [8 empty] | 0 |  | 0 | 0
| 14mm² THHN | Lm/s | 143 | 358.87 | 51318.41 | 0.0011905 |  | Lm/s | 0 | 0 |  | 0 | 0 | Ongoing
| 5.5mm² THHN | Lm/s | 3185 | 144.13 | 459054.05 | 0.010649 | 1000 | Lm/s | 144130 | 0 | 144130 | 0 | 0 | Ongoing
V. | Chipping & Restoration Works (Rough only) | lot | 1 | 145441.09 | 145441.09 | 0.003374 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VI. | Hangers & Supports | lot | 1 | 174529.31 | 174529.31 | 0.0040488 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VII. | Miscelleneuos | lot | 1 | 87264.66 | 87264.66 | 0.0020244 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
VIII. | Testing & Commissioning | lot | 1 | 884818.61 | 884818.61 | 0.020526 | 1 | lot | 0 | 0 |  | 0 | 0 | Ongoing
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 |  | 0 | 0 | Ongoing
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 |  | 0 | 0 | Ongoing
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 |  | 0 | 0 | Ongoing
| TOTAL PROJECT COST |  |  |  | 43106674.89 | 1 |  |  | 0 | 0 |  | 0 | 0
| Prepared by: |  | Reviewed and Submitted by: | [6 empty] | Noted by:
| PROJECT ENGINEER |  | PROJECT MANAGER | [6 empty] | PROJECT DIRECTOR